## Pillar C Tunnels
Control Account | Account | Supplier | Description in PRISM | Contract | NEW PHASE | CONTRACTS AND GROUPS | PILLAR | Sub Pillar | PBS_01 | PBS_02 | PBS_03 | PBS_04 | PBS Control Account ID | Project Sheet Lead/ Budget Holder | Commercial Lead/PM/ Responsible Person | NR VAT | YTD Actuals | ACWP cumulative to date | ETC | EAC (Current) | EAC (Previous) | EAC Current vs EAC Previous (Variance) | WMS Baseline | EAC Current vs WMS Baseline (Variance) | CURRENT BUDGET VS EAC (Variance) | CURRENT BUDGET | BASELINE | REMAINING BUDGET | In Month Actuals | In Month Forecast | In Month Variance | FY FORECAST | FY FORECAST (Previous) | FY FORECAST (Variance) | Prior Years cumulative to Mar-22 | 2022/23 | 2023/24 | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | 2031/32 | 2032/33 | 2033/34 | 2034/35 | 2035/36 | Apr-22 | May-22 | Jun-22 | Jul-22 | Aug-22 | Sep-22 | Oct-22 | Nov-22 | Dec-22 | Jan-23 | Feb-23 | Mar-23 | Apr-23 | May-23 | Jun-23 | Jul-23 | Aug-23 | Sep-23 | Oct-23 | Nov-23 | Dec-23 | Jan-24 | Feb-24 | Mar-24 | Apr-24 | May-24 | Jun-24 | Jul-24 | Aug-24 | Sep-24 | Oct-24 | Nov-24 | Dec-24 | Jan-25 | Feb-25 | Mar-25 | Apr-25 | May-25 | Jun-25 | Jul-25 | Aug-25 | Sep-25 | Oct-25 | Nov-25 | Dec-25 | Jan-26 | Feb-26 | Mar-26 | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27 | Apr-27 | May-27 | Jun-27 | Jul-27 | Aug-27 | Sep-27 | Oct-27 | Nov-27 | Dec-27 | Jan-28 | Feb-28 | Mar-28 | Apr-28 | May-28 | Jun-28 | Jul-28 | Aug-28 | Sep-28 | Oct-28 | Nov-28 | Dec-28 | Jan-29 | Feb-29 | Mar-29 | Apr-29 | May-29 | Jun-29 | Jul-29 | Aug-29 | Sep-29 | Oct-29 | Nov-29 | Dec-29 | Jan-30 | Feb-30 | Mar-30 | Apr-30 | May-30 | Jun-30 | Jul-30 | Aug-30 | Sep-30 | Oct-30 | Nov-30 | Dec-30 | Jan-31 | Feb-31 | Mar-31 | Apr-31 | May-31 | Jun-31 | Jul-31 | Aug-31 | Sep-31 | Oct-31 | Nov-31 | Dec-31 | Jan-32 | Feb-32 | Mar-32 | Apr-32 | May-32 | Jun-32 | Jul-32 | Aug-32 | Sep-32 | Oct-32 | Nov-32 | Dec-32 | Jan-33 | Feb-33 | Mar-33 | Apr-33 | May-33 | Jun-33 | Jul-33 | Aug-33 | Sep-33 | Oct-33 | Nov-33 | Dec-33 | Jan-34 | Feb-34 | Mar-34 | Apr-34 | May-34 | Jun-34 | Jul-34 | Aug-34 | Sep-34 | Oct-34 | Nov-34 | Dec-34 | Jan-35 | Feb-35 | Mar-35 | Apr-35 | May-35 | Jun-35 | Jul-35 | Aug-35 | Sep-35 | Oct-35 | Nov-35 | Dec-35 | Jan-36 | Feb-36 | Mar-36
Other Client Scope
540039.6.4097130.CEC100.540100 | Other Client Scope | CASCADE | Cascade - Error Correction 4097130 | C | EEW | CASC1 | C | CC0 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | David Tooze; Adam Buckingham; Eve Herrington | REC | 0 | 3730.04 | 0 | 3730.04 | 3730.04 | 0 |  | 3730.04 | 0 | 3730.04 | 3730.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3730.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.4097130.C01000.540100 | Other Client Scope | CASCADE | Statutory Procedures & Powers - COWI A/S ARCADIS CH2M JV - Pre-application | C | EEW | CASC1 | C | CC0 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | David Tooze; Adam Buckingham; Eve Herrington | REC | 0 | 9113.73 | 0 | 9113.73 | 9113.73 | 0 |  | 9113.73 | 0 | 9113.73 | 9113.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9113.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.4097130.C01000.540300 | Other Client Scope | CASCADE | Statutory Procedures & Powers - COWI A/S ARCADIS CH2M JV - July accounts to be updated | C | EEW | CASC1 | C | CC0 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | David Tooze; Adam Buckingham; Eve Herrington | REC | 0 | 2024.57 | 0 | 2024.57 | 2024.57 | 0 |  | 2024.57 | 0 | 2024.57 | 2024.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.4097130.C02000.210100 | Other Client Scope | CASCADE | Statutory Procedures & Powers - COWI A/S ARCADIS CH2M JV - July accounts to be updated | C | EEW | CASC1 | C | CC0 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | David Tooze; Adam Buckingham; Eve Herrington | REC | 0 | 28981.08 | 0 | 28981.08 | 28981.08 | 0 |  | 28981.08 | 0 | 28981.08 | 28981.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28981.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.4097130.C03000.210100 | Other Client Scope | CASCADE | Statutory Procedures & Powers - COWI A/S ARCADIS CH2M JV - Project Management | C | EEW | CASC1 | C | CC0 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | David Tooze; Adam Buckingham; Eve Herrington | REC | 0 | 702338.35 | 0 | 702338.35 | 702338.35 | 0 |  | 702338.35 | 0 | 702338.35 | 702338.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 702338.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.4097130.C03000.430100 | Other Client Scope | CASCADE | Statutory Procedures & Powers - COWI A/S ARCADIS CH2M JV - Environmental | C | EEW | CASC1 | C | CC0 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | David Tooze; Adam Buckingham; Eve Herrington | REC | 0 | 560.01 | 0 | 560.01 | 560.01 | 0 |  | 560.01 | 0 | 560.01 | 560.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 560.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.4097130.C03000.630100 | Other Client Scope | CASCADE | Statutory Procedures & Powers - COWI A/S ARCADIS CH2M JV - Ground Investigation | C | EEW | CASC1 | C | CC0 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | David Tooze; Adam Buckingham; Eve Herrington | REC | 0 | 2362899.72 | 0 | 2362899.72 | 2362899.72 | 0 |  | 2362899.72 | 0 | 2362899.72 | 2362899.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2362899.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.4097130.C03100.630100 | Other Client Scope | CASCADE | Statutory Procedures & Powers - COWI A/S ARCADIS CH2M JV - Ground Investigation | C | EEW | CASC1 | C | CC0 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | David Tooze; Adam Buckingham; Eve Herrington | REC | 0 | 9299.57 | 0 | 9299.57 | 9299.57 | 0 |  | 9299.57 | 0 | 9299.57 | 9299.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9299.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.4097130.C04000.540100 | Other Client Scope | CASCADE | Statutory Procedures & Powers - COWI A/S ARCADIS CH2M JV - Pre-application | C | EEW | CASC1 | C | CC0 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | David Tooze; Adam Buckingham; Eve Herrington | REC | 0 | 144648.5 | 0 | 144648.5 | 144648.5 | 0 |  | 144648.5 | 0 | 144648.5 | 144648.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144648.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.4097130.C05000.210100 | Other Client Scope | CASCADE | Statutory Procedures & Powers - COWI A/S ARCADIS CH2M JV - Project Management | C | EEW | CASC1 | C | CC0 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | David Tooze; Adam Buckingham; Eve Herrington | REC | 0 | 214695.82 | 0 | 214695.82 | 214695.82 | 0 |  | 214695.82 | 0 | 214695.82 | 214695.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 214695.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.4097130.C09000.210100 | Other Client Scope | CASCADE | Statutory Procedures & Powers - COWI A/S ARCADIS CH2M JV - Project Management | C | EEW | CASC1 | C | CC0 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | David Tooze; Adam Buckingham; Eve Herrington | REC | 0 | 86208.61 | 0 | 86208.61 | 86208.61 | 0 |  | 86208.61 | 0 | 86208.61 | 86208.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86208.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.4097130.C09000.630100 | Other Client Scope | CASCADE | Statutory Procedures & Powers - COWI A/S ARCADIS CH2M JV - Ground Investigation | C | EEW | CASC1 | C | CC0 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | David Tooze; Adam Buckingham; Eve Herrington | REC | 0 | 672.97 | 0 | 672.97 | 672.97 | 0 |  | 672.97 | 0 | 672.97 | 672.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 672.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.4097130.C09500.210100 | Other Client Scope | CASCADE | Statutory Procedures & Powers - COWI A/S ARCADIS CH2M JV - Project Management | C | EEW | CASC1 | C | CC0 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | David Tooze; Adam Buckingham; Eve Herrington | REC | 0 | 10474.14 | 0 | 10474.14 | 10474.14 | 0 |  | 10474.14 | 0 | 10474.14 | 10474.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10474.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.4097130.C48100.210100 | Other Client Scope | CASCADE | TO 48 - EW & GI - Enabling Works Delivery | C | EEW | CASC1 | C | CC3 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | David Tooze; Adam Buckingham; Eve Herrington | REC | 0 | 44816.265 | 0 | 44816.265 | 44816.265 | 0 |  | 44816.265 | 0.005 | 44816.27 | 44816.26 | 0.005 | 0 | 0 | 0 | 0 | 0 | 0 | 44816.265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.4097130.C48200.210300 | Other Client Scope | CASCADE | TO 48 - EW & GI - EW/GI Cost Estimating & Planning | C | EEW | CASC1 | C | CC3 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | David Tooze; Adam Buckingham; Eve Herrington | REC | 0 | 8.29 | 0 | 8.29 | 8.29 | 0 |  | 8.29 | 0 | 8.29 | 8.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.4097130.C48500.210100 | Other Client Scope | CASCADE | TO 48 - EW & GI - HE Enabling Works Delivery | C | EEW | CASC1 | C | CC3 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | David Tooze; Adam Buckingham; Eve Herrington | REC | 0 | 39367.58 | 0 | 39367.58 | 39367.58 | 0 |  | 39367.58 | 0 | 39367.58 | 39367.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39367.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.4097130.C48800.210100 | Other Client Scope | CASCADE | TO 48 - EW & GI - Project Controls | C | EEW | CASC1 | C | CC3 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | David Tooze; Adam Buckingham; Eve Herrington | REC | 0 | 2292.19 | 0 | 2292.19 | 2292.19 | 0 |  | 2292.19 | 0 | 2292.19 | 2292.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2292.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.9999999.C0R800.210100 | Other Client Scope | Cascade Uninstructed Adv Works | Cascade Uninstructed Works Advanced Works | F | EEW | CASC1 | C | CC0 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | David Tooze; Adam Buckingham; Eve Herrington | REC | 0 | 0 | 7098159.7694 | 7098159.7694 | 7098159.7694 | 0 | 21641885.5408 | -14543725.7714 | -7098159.7694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7098159.7694 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7098159.7694
540039.6.4101290.C00000.210100 | Other Client Scope | MOTT MACDONALD | Construction, Commissioning & H/O - MOTT MACDONALD GROUP LTD - Project Management | X | EEW | COMMO | C | CS1 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | David Carpenter | HYB | 0 | 412123.75 | 0 | 412123.75 | 412123.75 | 0 |  | 412123.75 | 0 | 412123.75 | 412123.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 412123.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.0000000.C00000.210100 | Other Client Scope | A-ONE + INTEGRATED | Construction, Commissioning & H/O - A-ONE + INTEGRATED HIGHWAY SERVICES (CIS) | X | EEW | HEPOS | C | C03 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | Closed Account | REC | 0 | 15647.52 | 0 | 15647.52 | 15647.52 | 0 |  | 15647.52 | 0 | 15647.52 | 15647.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15647.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.9999999.C09600 | Other Client Scope | Gravesend Ferry | Gravesend Ferry | F | EEW | HEPOS | C | CS1 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac |  | REC | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.4105142.C000M3.210100 | Other Client Scope | Osborne Clarke LLP | Construction, Commissioning & H/O - Osborne Clarke LLP - Project Management | X | EEW | HEPOS | C | C03 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac |  | REC | 0 | 1285.2 | 0 | 1285.2 | 1285.2 | 0 |  | 1285.2 | 0 | 1285.2 | 1285.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1285.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.9999999.C07100 | Other Client Scope | ITS | ITS | F | CON | ITSIT | C | C07 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac |  | HYB | 0 | 0 | 9501588.0129 | 9501588.0129 | 9501588.0129 | 0 |  | 9501588.0129 | 380385.8271 | 9881973.84 | 9501588.07 | 9881973.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 771753.4567 | 1393165.331 | 1443279.1918 | 1443279.1918 | 1443279.1918 | 1443279.1918 | 1443279.1918 | 120273.266 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70159.4052 | 70159.4052 | 70159.4052 | 70159.4052 | 70159.4052 | 70159.4052 | 70159.4052 | 70159.4052 | 70159.4052 | 70159.4052 | 70159.4052 | 70159.4052 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.9999999.C03000 | Other Client Scope | Cost Items for which there are no agreements / control accounts | Cost items for which there are no agreements / control accounts | X | EEW | TPPSS | C | C03 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac |  | HYB | 0 | 1.4552e-11 | 0 | 1.4552e-11 | 1.4552e-11 | 0 |  | 1.4552e-11 | -1.4552e-11 | 0 | 0 | -1.4552e-11 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4552e-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.9999999.C03700 | Other Client Scope | Ingrebourne Valley Limited | Ingebourne Valley Limited | X | EEW | TPOTH | C | CL1 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | Natasha Juckes; Matt Page | HYB | 0 | 2.9104e-10 | 0 | 2.9104e-10 | 2.9104e-10 | 0 |  | 2.9104e-10 | -2.9104e-10 | 0 | 0 | -2.9104e-10 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9104e-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.XXXXXXX.C00100.D1Y046 | Other Client Scope | NORTHUMBRIAN WATER | Northumbrian Water | C | EEW | STATS | C | C03 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | Warren Pavett/Shauna Dellar | HYB | 0 | 162642.0004 | 75000 | 237642.0004 | 237642.0004 | 0 |  | 237642.0004 | -85000.0004 | 152642 | 188805.49 | -10000.0004 | 0 | 0 | 0 | 0 | 0 | 0 | 150642.0004 | 0 | 12000 | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37500 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.4105716.C002M3.D1Y046 | Other Client Scope | SOUTHERN WATER | Southern Water - Advanced Construction Works | C | EEW | STATS | C | C03 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | Warren Pavett/Shauna Dellar | HYB | 0 | 2750 | 0 | 2750 | 2750 | 0 |  | 2750 | 0 | 2750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.4103431.CEC1M3.D1Y041 | Other Client Scope | UK POWER NETWORKS | UK Power Networks - Error Correction 4103431 | X | EEW | STATS | C | C03 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | Warren Pavett/Shauna Dellar | HYB | 0 | 2.9104e-11 | 0 | 2.9104e-11 | 2.9104e-11 | 0 |  | 2.9104e-11 | -2.9104e-11 | 0 | 0 | -2.9104e-11 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9104e-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.4106851.C000M3.D1Y041 | Other Client Scope | UK POWER NETWORKS | Construction, Commissioning & H/O - UK POWER NETWORKS (OPERATIONS) LTD (CIS) DIVERT/CONNECT - Utilit | X | EEW | STATS | C | C03 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | Warren Pavett/Shauna Dellar | HYB | 0 | 0.0018877 | 0 | 0.0018877 | 0.0018877 | 0 |  | 0.0018877 | -0.0018877 | 0 | 496983.21 | -0.0018877 | 0 | 0 | 0 | 0 | 0 | 0 | 86788.3419 | -86788.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | -86788.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.4107471.C000M3.210100 | Other Client Scope | INGREBOURNE VALLEY LTD | Construction, Commissioning & H/O - INGREBOURNE VALLEY LTD - Project Management | C | EEW | TPOTH | C | CL1 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | Natasha Juckes; Matt Page | HYB | 0 | 286555.794 | 331572.0572 | 618127.8512 | 618127.8512 | 0 |  | 618127.8512 | -278469.3212 | 339658.53 | 85000 | 53102.736 | 0 | 0 | 0 | 331572.0572 | 331572.0572 | 0 | 113861.625 | 160019.6681 | 12674.5009 | 331572.0572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97000 | 84100 | -159450.65 | 50000 | 46410.75 | 49886.79 | 31975.3612 | -50332.07 | 0 | 0 | 4565.668 | 5863.8188 | 21669.0815 | 15160.8585 | 28947.2933 | -53102.8296 | 111860.5122 | 113839.455 | -225699.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75233.29 | 75233.29 | 181105.4772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.4.XXXXXXX.C10000.220300 | Other Client Scope |  | Development Phase (excl. ECI) - PCF Stage 4: Surveys (GI, ATT, UTT) |  |  | TPOTH | C | CC0 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 2806319.01 | 2806319.01 | 12302517.86 | 2806319.01 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.4.XXXXXXX.C20000.220300 | Other Client Scope |  | Development Phase (excl. ECI) - PCF Stage 4: SU & NRTS design |  |  | TPOTH | C | CC0 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 3205949.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.5.XXXXXXX.C10000.220300 | Other Client Scope |  | Development Phase (excl. ECI) - PCF Stage 5: Surveys (GI, ATT, UTT) |  |  | TPOTH | C | CC0 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 633236.13 | 633236.13 | 0 | 633236.13 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.5.XXXXXXX.C20000.220300 | Other Client Scope |  | Development Phase (excl. ECI) - PCF Stage 5: SU & NRTS design |  |  | TPOTH | C | CC0 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 2014421.61 | 2014421.61 | 5023496.24 | 2014421.61 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.4098871.CEC100.D1Y044 | Other Client Scope | HS1 LIMITED | HS1 - Error Correction 4098871 | X | EEW | TPRAI | C | C03 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | Bob Jheeta / Warren Pavett | HYB | 0 | 2430 | 0 | 2430 | 2430 | 0 |  | 2430 | 0 | 2430 | 2430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.4100145.CEC100.D1Y044 | Other Client Scope | NETWORK RAIL | Network Rail - Error Correction 4100145 | C | EEW | TPRAI | C | C03 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | Bob Jheeta / Warren Pavett | HYB | 6156 | 71755.5438 | 18244.46 | 90000.0038 | 90000.0038 | 0 |  | 90000.0038 | -45000.0038 | 45000 | 20000 | -26755.5438 | 3078 | 3078 | 0 | 24400.46 | 24400.46 | 0 | 60000 | -30000 | 35599.5438 | 24400.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6000 | 6000 | 6000 | -48000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | -17478.4562 | 3078 | 3078 | 3078 | 3078 | 3078 | 3078 | 3078 | 3078 | 2854.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Inflation
540039.6.9999999.C09200.C3X020 | Project Inflation | Tunnels Inflation on Base | Tunnels Inflation on Base | F | CON | INFLA | C | C09 | TN | CT | PL | IN2 | 540039.TN.CT.PL.IN2 | Sinisa Galac |  | INCL. | 357196.1898 | 872371.9998 | 737900588.8953 | 738772960.8951 | 738772960.8945 | 0.00061178 |  | 738772960.8951 | -233761622.5851 | 505011338.31 | 546871114.82 | 504138966.3102 | 170008.7806 | 182338.4197 | -12329.6392 | 2911480.5823 | 2911470.0777 | 10.5047 | 0 | 0 | 515175.81 | 2911480.5823 | 3449008.8662 | 63628680.2681 | 123694930.1183 | 101593862.5587 | 114310650.406 | 136195974.2004 | 142134851.1718 | 19469654.4596 | 13978680.5284 | 0 | 16890011.9252 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132142.99 | 208774.18 | 174258.64 | 187187.4093 | 170008.7806 | 218953.17 | 190409.1109 | 217004.8715 | 208526.2477 | 253744.066 | 260822.8354 | 258728.4456 | 358466.3446 | 280436.7661 | 307192.5347 | 195307.1244 | 180792.5355 | 128947.1649 | 245855.2728 | 252608.7687 | 265567.0099 | 347969.5434 | 364498.1411 | 377295.9493 | 376749.8306 | 349329.2178 | 364088.308 | 281895.1323 | 252096.7966 | 248033.0306 | 250735.1838 | 1808254.5665 | 1808254.5665 | 6688195.4647 | 6688195.4647 | 6688195.4647 | 12971608.1992 | 12971608.1992 | 12971608.1992 | 13127162.4025 | 13127162.4025 | 13127162.4025 | 9801490.9059 | 9801490.9059 | 9801490.9059 | 8576003.4658 | 8576003.4658 | 8576003.4658 | 9726986.5985 | 9726986.5985 | 9726986.5985 | 10032430.6943 | 10032430.6943 | 10032430.6943 | 9157521.5699 | 9157521.5699 | 9157521.5699 | 7087310.2524 | 7087310.2524 | 7087310.2524 | 7587358.3364 | 7587358.3364 | 7587358.3364 | 8780249.7456 | 8780249.7456 | 8780249.7456 | 9567910.0024 | 9567910.0024 | 9567910.0024 | 10065652.4582 | 10065652.4582 | 10065652.4582 | 9689737.9292 | 9689737.9292 | 9689737.9292 | 10506702.0062 | 10506702.0062 | 10506702.0062 | 9823502.8458 | 9823502.8458 | 9823502.8458 | 11904390.029 | 11904390.029 | 11904390.029 | 13164063.1857 | 13164063.1857 | 13164063.1857 | 13338251.724 | 13338251.724 | 13338251.724 | 10916391.7561 | 10916391.7561 | 10916391.7561 | 8995410.777 | 8995410.777 | 8995410.777 | 14128229.4668 | 14128229.4668 | 14128229.4668 | 3329189.0277 | 3329189.0277 | 3329189.0277 | 984921.4901 | 984921.4901 | 984921.4901 | 803603.8631 | 803603.8631 | 803603.8631 | 1372170.439 | 1372170.439 | 1372170.439 | 1751108.9527 | 1751108.9527 | 1751108.9527 | 1798701.8386 | 1798701.8386 | 1798701.8386 | 551277.0587 | 551277.0587 | 551277.0587 | 558472.3261 | 558472.3261 | 558472.3261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16890011.9252
540039.6.9999999.C09600.C3X020 | Project Inflation | Tunnels Inflation on Risk | Tunnels Inflation on Risk | F | CON | INFLA | C | C09 | TN | CT | PL | IN2 | 540039.TN.CT.PL.IN2 | Sinisa Galac |  | INCL. | 0 | 0 | 0 | 0 | 0 | 0 | 738772960.8917 | -738772960.8917 | 59196049.86 | 59196049.86 | 144423893.38 | 59196049.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.9999999.C01X00 | Project Inflation | Finance/ Programme Overlay | Tunnels Overlay | F | EEW | OVER1 | C | C24 | TN | CT | PL | IN2 | 540039.TN.CT.PL.IN2 | Paul Williamson |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Main Works - Fee
540039.6.TUN.FEE | Contractor Fee | Tunnels Fee | Tunnels Fee | F | CON | MWSTU | C | C04 | TN | DP | P2 | FEE | 540039.TN.DP.P2.FEE |  |  |  | 0 | 0 | 143770109.2267 | 143770109.2267 | 143770109.2267 | 0 | 143770109.2292 | -0.00252 | -143770109.2267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 17762540.4722 | 31621085.9824 | 21190778.3594 | 21690020.3058 | 24205399.9979 | 24344805.4151 | 2955478.6939 | 0 | 0 | 0 | [26 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 547370.0329 | 547370.0329 | 2025885.7949 | 2025885.7949 | 2025885.7949 | 3530047.6739 | 3530047.6739 | 3530047.6739 | 3370033.7975 | 3370033.7975 | 3370033.7975 | 2234697.3092 | 2234697.3092 | 2234697.3092 | 3845088.0216 | 2084423.8363 | 2084423.8363 | 2264318.9894 | 2264318.9894 | 2264318.9894 | 2200681.7721 | 2200681.7721 | 2200681.7721 | 1912530.2515 | 1912530.2515 | 1912530.2515 | 1436419.2679 | 1436419.2679 | 1436419.2679 | 1513961.4949 | 1513961.4949 | 1513961.4949 | 1731177.5809 | 1731177.5809 | 1731177.5809 | 1818242.0953 | 1818242.0953 | 1818242.0953 | 1893337.9807 | 1893337.9807 | 1893337.9807 | 1787249.1118 | 1787249.1118 | 1787249.1118 | 1910990.5315 | 1910990.5315 | 1910990.5315 | 1710368.8648 | 1710368.8648 | 1710368.8648 | 2076556.2035 | 2076556.2035 | 2076556.2035 | 2370551.0661 | 2370551.0661 | 2370551.0661 | 2362185.6539 | 2362185.6539 | 2362185.6539 | 1864481.5892 | 1864481.5892 | 1864481.5892 | 1525333.9223 | 1525333.9223 | 1525333.9223 | 2362933.973 | 2362933.973 | 2362933.973 | 548145.7065 | 548145.7367 | 548145.7367 | 145068.5855 | 145068.5855 | 145068.5855 | 105998.1061 | 105998.1061 | 105998.1061 | 557841.4393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Main Works - Tunnels (Phase 1)
540039.5.9999999.C04700.820000 | Stage 1 Scope | MWC Detailed Design and ECI | Phase 1 - Mobilisation Phase | X | CON | MWSTU | C | C11 | TN | DP | P1 | PH1 | 540039.TN.DP.P1.PH1 | Sinisa Galac | Sinisa Galac/ Natasha Juckes | HYB | 3394890 | 9103581.04 | 50780893.32 | 59884474.36 | 59884474.36 | 0 | 59884474.36 | 0 | 1160154.77 | 61044629.13 | 28428936.57 | 51941048.09 | 1615810 | 1727284 | -111474 | 27320560.2 | 27320560.2 | 0 | 0 | 0 | 5708691.04 | 27320560.2 | 18916923.01 | 7938300.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1632700 | 2000956.83 | 2075034.21 | 1779080 | 1615810 | 2070714 | 1797794 | 2045526 | 1932364 | 2383955 | 2446420.4 | 2422774.4 | 3351201.2 | 2617401.73 | 2857519.47 | 1808999.33 | 1671203.52 | 1187729.93 | 1474442.09 | 1533101.05 | 1648806.05 | 1496896.52 | 1615110.07 | 1724700.55 | 1713983.86 | 1464507.24 | 1577442.8 | 1902786.11 | 2037046 | 2001070 | 1997398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DP Risk
540039.6.9999999.C12R00.C3X010 | Risk Quota | RISK | TU- Contractor/Delivery Partner Risk- Construction- Threats | F | CON | MWSTU | C | C12 | TN | DP | P2 | RK4 | 540039.TN.DP.P2.RK4 | Sinisa Galac |  | HYB | 0 | 0 | 39780445 | 39780445 | 39780445 | 0 | 39780445 | 0 | 163923784.49 | 203704229.49 | 298877439.79 | 203704229.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2652489.28 | 8038258.29 | 6568445.67 | 6722762.97 | 7500274.89 | 7543365.6 | 754848.3 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25560.65 | 25560.65 | 316120.57 | 316120.57 | 316120.57 | 551002.09 | 551002.09 | 551002.09 | 651961.51 | 651961.51 | 651961.51 | 680196.21 | 680196.21 | 680196.21 | 645827.77 | 645827.77 | 645827.77 | 701433.94 | 701433.94 | 701433.94 | 681763.47 | 681763.47 | 681763.47 | 592694.91 | 592694.91 | 592694.91 | 445527.48 | 445527.48 | 445527.48 | 469496.03 | 469496.03 | 469496.03 | 536638.22 | 536638.22 | 536638.22 | 563550.14 | 563550.14 | 563550.14 | 586762.52 | 586762.52 | 586762.52 | 553970.11 | 553970.11 | 553970.11 | 592218.98 | 592218.98 | 592218.98 | 530206.18 | 530206.18 | 530206.18 | 643395.86 | 643395.86 | 643395.86 | 734270.61 | 734270.61 | 734270.61 | 731684.84 | 731684.84 | 731684.84 | 577842.92 | 577842.92 | 577842.92 | 473011.29 | 473011.29 | 473011.29 | 731916.15 | 731916.15 | 731916.15 | 170959.05 | 170959.29 | 170959.29 | 46366.85 | 46366.85 | 46366.85 | 34290.04 | 34290.04 | 34290.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DP Opportunities
540039.6.9999999.C12O00.C3X010 | Risk Quota | RISK | TU- Contractor/Delivery Partner Risk- Construction- Opportunities | F | CON | MWSTU | C | C12 | TN | DP | P2 | OP4 | 540039.TN.DP.P2.OP4 | Sinisa Galac |  | HYB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -11528401.95 | -11528401.95 | 0 | -11528401.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Risk
540039.6.9999999.C12R00.R11000 | Project Risk | RISK | TU- Employer Risk- Threats | F | CON | RSK01 | C | C12 | TN | CT | PL | RK3 | 540039.TN.CT.PL.RK3 | Sinisa Galac |  | HYB | 0 | 0 | 185105983.9862 | 185105983.9862 | 185105983.9862 | 0 | 185105983.9862 | 0 | -110391923.1662 | 74714060.82 | 8396602.39 | 74714060.82 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 111530.4027 | 11902250.0904 | 34179067.738 | 27794368.0731 | 28421648.6613 | 31296861.6067 | 30609009.1218 | 8938823.4433 | 11852424.8488 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9638.4299 | 9638.4299 | 9638.4299 | 13769.1855 | 13769.1855 | 13769.1855 | 13769.1855 | 13769.1855 | 13769.1855 | 98060.8767 | 98060.8767 | 98060.8767 | 98060.8767 | 98060.8767 | 98060.8767 | 1280062.2444 | 1280062.2444 | 1280062.2444 | 2491232.699 | 2491232.699 | 2491232.699 | 2904663.1747 | 2904663.1747 | 2904663.1747 | 3019522.2883 | 3019522.2883 | 3019522.2883 | 2621315.2651 | 2621315.2651 | 2621315.2651 | 2847521.8512 | 2847521.8512 | 2847521.8512 | 2863030.7427 | 2863030.7427 | 2863030.7427 | 2500537.3816 | 2500537.3816 | 2500537.3816 | 1901858.4339 | 1901858.4339 | 1901858.4339 | 1999362.7994 | 1999362.7994 | 1999362.7994 | 2272498.0596 | 2272498.0596 | 2272498.0596 | 2381976.088 | 2381976.088 | 2381976.088 | 2476404.3352 | 2476404.3352 | 2476404.3352 | 2343004.4044 | 2343004.4044 | 2343004.4044 | 2498601.283 | 2498601.283 | 2498601.283 | 2246332.4369 | 2246332.4369 | 2246332.4369 | 2706789.4684 | 2706789.4684 | 2706789.4684 | 2980564.0139 | 2980564.0139 | 2980564.0139 | 2970045.0442 | 2970045.0442 | 2970045.0442 | 2344214.1864 | 2344214.1864 | 2344214.1864 | 1917757.8027 | 1917757.8027 | 1917757.8027 | 2970986.0072 | 2970986.0072 | 2970986.0072 | 689006.4953 | 689006.4953 | 689006.4953 | 182162.8968 | 182162.8968 | 182162.8968 | 133034.2809 | 133034.2809 | 133034.2809 | 1975404.1415 | 1975404.1415 | 1975404.1415 | 1975404.1415 | 1975404.1415 | 1975404.1415 | 1975404.1415 | 1975404.1415 | 1975404.1415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.9999999.C12R06.R11000 | Project Risk | RISK | TU- Employer Risk- National Highways Stage 6 Fee Adj | F | CON | MWSTU | C | C12 | TN | CT | PL | RK3 | 540039.TN.CT.PL.RK3 | Sinisa Galac |  | HYB | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | -6593333.13 | -6593333.13 | 0 | -6593333.13 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Opportunities
540039.6.9999999.C12O00.R14000 | Project Opportunities | RISK | TU- Employer Risk- Opportunities | F | CON | RSK01 | C | C12 | TN | CT | PL | OP3 | 540039.TN.CT.PL.OP3 | Sinisa Galac |  | HYB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -104801218.02 | -104801218.02 | 0 | -104801218.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Incentives
540039.6.9999999.C16000.C3X060 | Incentives | Tunnels - Incentives | Tunnels - Incentives | F | CON | MWSTU | C | C16 | TN | DP | PL | INS | 540039.TN.DP.PL.INS | Sinisa Galac | Sinisa Galac/ Natasha Juckes | HYB | 0 | 0 | 24500000.02 | 24500000.02 | 24500000.02 | 0 | 24500000 | 0.02 | -24500000.02 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 2416666.67 | 2416666.67 | 2416666.67 | 2416666.67 | 2416666.67 | 11416666.67 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2416666.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2416666.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2416666.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2416666.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2416666.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 0 | 0 | 5000000 | 2416666.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Stats Undertakers (Utilities)
540039.6.4104809.C00000.D1Y046 | Utilities (Client) | ANGLIAN WATER | Anglian Water | F | EEW | STATS | C | C03 | TN | CT | PL | UTN | 540039.TN.CT.PL.UTN | Sinisa Galac | Warren Pavett/Shauna Dellar | HYB | 600 | 6600 | 10200 | 16800 | 16800 | 0 |  | 16800 | -14400 | 2400 | 0 | -4200 | 600 | 600 | 0 | 3600 | 3600 | 0 | 0 | 0 | 6000 | 3600 | 3600 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 600 | 1200 | 600 | 600 | 600 | 0 | 600 | 0 | 600 | 0 | 600 | 0 | 600 | 0 | 600 | 0 | 600 | 0 | 600 | 0 | 600 | 0 | 600 | 0 | 600 | 0 | 600 | 0 | 600 | 0 | 600 | 0 | 600 | 0 | 600 | 0 | 600 | 0 | 600 | 0 | 600 | 0 | 600 | 0 | 600 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.4101428.C000M3.D1Y045 | Utilities (Client) | BT OPENREACH early design | BT OPENREACH EARLY DESIGN - Utilities Telecoms | X | EEW | STATS | C | C03 | [5 empty] | Sinisa Galac | Warren Pavett/Shauna Dellar | HYB | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.4108361.C000M3.D1Y041 | Utilities (Client) | UK POWER NETWORKS | Construction, Commissioning & H/O - UK POWER NETWORKS (OPERATIONS) LTD (CIS) DIVERT/CONNECT - Utilit | C | EEW | STATS | C | C03 | TN | CT | PL | UTN | 540039.TN.CT.PL.UTN | Sinisa Galac | Warren Pavett/Shauna Dellar | HYB | 0 | 1021963.8277 | 53571915.6988 | 54593879.5265 | 54593879.5265 | 0 | 54610679.5265 | -16800 | -53449621.3265 | 1144258.2 | 0 | 122294.3723 | 0 | 0 | 0 | 0 | 0 | 0 | 569438.6804 | 589819.5173 | -137294.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53571915.6988 | 167473.99 | 117504.8673 | 124512 | 133639.97 | 114820.44 | 78663.25 | 84906 | 35669 | 52788 | 39447 | 45000 | -404605 | 0 | 0 | -15000 | 0 | 0 | -291783.87 | 56496.5 | 56496.5 | 56496.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53571915.6988
540039.6.4108361.C001M3.D1Y041 | Utilities (Client) | UK POWER NETWORKS | UK POWER NETWORKS | C | CON | STATS | C | C03 | TN | CT | PL | UTN | 540039.TN.CT.PL.UTN | Sinisa Galac | Warren Pavett/Shauna Dellar | HYB | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 200000 | 200000 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | -200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | -200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.9999999.C09500 | Utilities (Client) | Utilites General | Utilities General | X | EEW | STATS | C | C03 | [5 empty] | Sinisa Galac | Future | HYB | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.5.XXXXXXX.C00100.D1Y046 | Utilities (Client) | Essex and Suffolk Water | Essex & Suffolk Water | U | EEW | STATS | C | C03 | [5 empty] | Sinisa Galac | Warren Pavett/Shauna Dellar | HYB | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.5.XXXXXXX.C00100.D1Y041 | Utilities (Client) | UK POWER NETWORKS | UKPN | U | EEW | STATS | C | C03 | [5 empty] | Sinisa Galac | Warren Pavett/Shauna Dellar | HYB | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Main Works
540039.6.9999999.C00000.C10153 | Stage 2 Unlet Works | Main Works Advanced Works | Main Works Advanced works | F | CON | MWSTU | C | C10 | TN | DP | P2 | P2U | 540039.TN.DP.P2.P2U | Sinisa Galac | Sinisa Galac/ Natasha Juckes | HYB | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 62687753.82 | 62687753.82 | 44603439.12 | 62687753.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.9999999.C05500.D1Y043 | Stage 2 Unlet Works | Construction TBA | TU - SU Contestable works | F | CON | MWSTU | C | C05 | TN | DP | P2 | P2U | 540039.TN.DP.P2.P2U | Sinisa Galac | Sinisa Galac/ Natasha Juckes | HYB | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 17980170 | 17980170 | 28285.49 | 17980170 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.9999999.C04100.C10000 | Stage 2 Unlet Works | Phase 2 - Construction Phase | Phase 2 - Construction Phase | F | CON | MWSTU | C | C04 | TN | DP | P2 | P2U | 540039.TN.DP.P2.P2U | Sinisa Galac | Sinisa Galac/ Natasha Juckes | HYB | 0 | 0 | 1101252167.91 | 1101252167.91 | 1101252167.91 | 0 | 1101841055.1091 | -588887.1991 | 329280628.95 | 1430532796.86 | 1332008126.45 | 1430532796.86 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 138320054.15 | 242922741.57 | 161612334.96 | 165420255.33 | 184606074.3 | 185669375.79 | 22701331.81 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4318645.96 | 4318645.96 | 15762338.12 | 15762338.12 | 15762338.12 | 27465249.29 | 27465249.29 | 27465249.29 | 26094338.47 | 26094338.47 | 26094338.47 | 17055496.72 | 17055496.72 | 17055496.72 | 29870743.83 | 15897218.55 | 15897218.55 | 17269351.69 | 17269351.69 | 17269351.69 | 16783964.88 | 16783964.88 | 16783964.88 | 14586116.61 | 14586116.61 | 14586116.61 | 10954625.44 | 10954625.44 | 10954625.44 | 11546071.39 | 11546071.39 | 11546071.39 | 13202866.39 | 13202866.39 | 13202866.39 | 13866942.68 | 13866942.68 | 13866942.68 | 14439729.39 | 14439729.39 | 14439729.39 | 13630546.65 | 13630546.65 | 13630546.65 | 14574372.54 | 14574372.54 | 14574372.54 | 13044149.89 | 13044149.89 | 13044149.89 | 15837208.93 | 15837208.93 | 15837208.93 | 18079626.74 | 18079626.74 | 18079626.74 | 18015820.35 | 18015820.35 | 18015820.35 | 14219630.01 | 14219630.01 | 14219630.01 | 11632813.49 | 11632813.49 | 11632813.49 | 18021528.08 | 18021528.08 | 18021528.08 | 4179403.7 | 4179403.7 | 4179403.7 | 1104971.13 | 1104971.13 | 1104971.13 | 806964.77 | 806964.77 | 806964.77 | 4427313.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.TU.TBC001 | Stage 2 Unlet Works | Stage 2 Early Works - Utilities & Programme De-risking | Stage 2 Early Works - Utilities & Programme De-risking | F | CON | MWSTU | C | C04 | TN | DP | P2 | P2U | 540039.TN.DP.P2.P2U | Sinisa Galac | Sinisa Galac/ Natasha Juckes | HYB | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 5160000 | -5160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [42 empty] | 860000 | 860000 | 860000 | 860000 | 860000 | 860000 | [6 empty] | -860000 | -860000 | -860000 | -860000 | -860000 | -860000
540039.6.9999999.C00200.C3X040 | Stage 2 Unlet Works | Contractor Fee - Tunnels | Contractor's fee - Prelims | F | CON | MWSTU | C | C04 | TN | DP | P2 | P2U | 540039.TN.DP.P2.P2U | Sinisa Galac | Sinisa Galac/ Natasha Juckes | HYB | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.9999999.C00300.C3X040 | Stage 2 Unlet Works | Contractor Fee - Tunnels | Contractor's fee - Direct Works | F | CON | MWSTU | C | C04 | TN | DP | P2 | P2U | 540039.TN.DP.P2.P2U | Sinisa Galac | Sinisa Galac/ Natasha Juckes | HYB | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 187371420.24 | 187371420.24 | 168941892.48 | 187371420.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.9999999.C00500.D1Y110 | Stage 2 Unlet Works | Environment Authority costs | Environment Authority costs | F | CON | TPOTH | C | C06 | TN | DP | P2 | P2U | 540039.TN.DP.P2.P2U | Sinisa Galac |  | HYB | 0 | 0 | 165507.4783 | 165507.4783 | 165507.4783 | 0 |  | 165507.4783 | -165507.4783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23543.2128 | 36701.1075 | 78947.3684 | 26315.7895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1961.9344 | 1961.9344 | 1961.9344 | 1961.9344 | 1961.9344 | 1961.9344 | 1961.9344 | 1961.9344 | 1961.9344 | 1961.9344 | 1961.9344 | 1961.9344 | 3058.4256 | 3058.4256 | 3058.4256 | 3058.4256 | 3058.4256 | 3058.4256 | 3058.4256 | 3058.4256 | 3058.4256 | 3058.4256 | 3058.4256 | 3058.4256 | 6578.9474 | 6578.9474 | 6578.9474 | 6578.9474 | 6578.9474 | 6578.9474 | 6578.9474 | 6578.9474 | 6578.9474 | 6578.9474 | 6578.9474 | 6578.9474 | 2192.9825 | 2192.9825 | 2192.9825 | 2192.9825 | 2192.9825 | 2192.9825 | 2192.9825 | 2192.9825 | 2192.9825 | 2192.9825 | 2192.9825 | 2192.9825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.9999999.C00500.C22700 | Stage 2 Unlet Works | Work for Local Authorities | Work for Local Authorities | X | CON | STATS | C | C05 | TN | DP | P2 | P2U | 540039.TN.DP.P2.P2U | Sinisa Galac | Future | HYB | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 783808.74 | 783808.74 | 7752578.48 | 783808.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.9999999.C06100.D1Y044 | Stage 2 Unlet Works | Rail Authority costs | Rail Authority costs | X | CON | TPRAI | C | C06 | TN | DP | P2 | P2U | 540039.TN.DP.P2.P2U | Sinisa Galac | Bob Jheeta / Warren Pavett | HYB | 0 | 0 | 158887.1791 | 158887.1791 | 158887.1791 | 0 |  | 158887.1791 | -158887.1791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22601.4843 | 35233.0632 | 75789.4737 | 25263.1579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1883.457 | 1883.457 | 1883.457 | 1883.457 | 1883.457 | 1883.457 | 1883.457 | 1883.457 | 1883.457 | 1883.457 | 1883.457 | 1883.457 | 2936.0886 | 2936.0886 | 2936.0886 | 2936.0886 | 2936.0886 | 2936.0886 | 2936.0886 | 2936.0886 | 2936.0886 | 2936.0886 | 2936.0886 | 2936.0886 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 2105.2632 | 2105.2632 | 2105.2632 | 2105.2632 | 2105.2632 | 2105.2632 | 2105.2632 | 2105.2632 | 2105.2632 | 2105.2632 | 2105.2632 | 2105.2632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.9999999.C00500.D1Y041 | Stage 2 Unlet Works | TBC - future stages | TU- Non- Contestable- Construction, Utilities Power | F | CON | STATS | C | C11 | TN | DP | P2 | P2U | 540039.TN.DP.P2.P2U | Sinisa Galac | Future | HYB | 0 | 0 | 11069466.5337 | 11069466.5337 | 11069466.5337 | 0 |  | 11069466.5337 | 0.066252 | 11069466.6 | 0 | 11069466.6 | 0 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 30000 | 7054658.8038 | 59183.9395 | 1977811.8952 | 1977811.8952 | 0 | 0 | 0 | 0 | 0 | 0 | -30000 | [29 empty] | 30000 | [9 empty] | 783850.9782 | 783850.9782 | 783850.9782 | 783850.9782 | 783850.9782 | 783850.9782 | 783850.9782 | 783850.9782 | 783850.9782 | 0 | 0 | 0 | 19727.9798 | 19727.9798 | 19727.9798 | 0 | 0 | 0 | 0 | 0 | 0 | 164817.6579 | 164817.6579 | 164817.6579 | 164817.6579 | 164817.6579 | 164817.6579 | 164817.6579 | 164817.6579 | 164817.6579 | 164817.6579 | 164817.6579 | 164817.6579 | 164817.6579 | 164817.6579 | 164817.6579 | 164817.6579 | 164817.6579 | 164817.6579 | 164817.6579 | 164817.6579 | 164817.6579 | 164817.6579 | 164817.6579 | 164817.6579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [47 empty] | -30000
540039.6.9999999.C00500.D1Y045 | Stage 2 Unlet Works | TBC - future stages | TU- Non- Contestable- Construction, Utilities Telecoms | F | CON | STATS | C | C12 | TN | DP | P2 | P2U | 540039.TN.DP.P2.P2U | Sinisa Galac | Future | HYB | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 152640.75 | 152640.75 | 0 | 152640.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.9999999.C00500.D1Y046 | Stage 2 Unlet Works | TBC - future stages | TU- Non- Contestable- Construction, Utilities Water | F | CON | STATS | C | C13 | TN | DP | P2 | P2U | 540039.TN.DP.P2.P2U | Sinisa Galac | Future | HYB | 0 | 0 | 167114 | 167114 | 167114 | 0 |  | 167114 | -1492.85 | 165621.15 | 167114.01 | 165621.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48117.8306 | 84626.2905 | 34369.879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4009.8192 | 4009.8192 | 4009.8192 | 4009.8192 | 4009.8192 | 4009.8192 | 4009.8192 | 4009.8192 | 4009.8192 | 4009.8192 | 4009.8192 | 4009.8192 | 7052.1909 | 7052.1909 | 7052.1909 | 7052.1909 | 7052.1909 | 7052.1909 | 7052.1909 | 7052.1909 | 7052.1909 | 7052.1909 | 7052.1909 | 7052.1909 | 2864.1566 | 2864.1566 | 2864.1566 | 2864.1566 | 2864.1566 | 2864.1566 | 2864.1566 | 2864.1566 | 2864.1566 | 2864.1566 | 2864.1566 | 2864.1566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.9999999.C00500.D1Y043 | Stage 2 Unlet Works | TBC - future stages | TU- Non- Contestable Others- (Nominate - new connections) CA03 and CA05 | F | CON | STATS | C | C13 | TN | DP | P2 | P2U | 540039.TN.DP.P2.P2U | Sinisa Galac | Future | HYB | 0 | 0 | -10972087.99 | -10972087.99 | -10972087.99 | 0 |  | -10972087.99 | 30561291.73 | 19589203.74 | 13901634.25 | 19589203.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410779.1886 | 3165138.0422 | 9610582.2821 | 5488537.6915 | 890418.6936 | 23747.842 | 0 | 0 | 0 | 0 | -30561291.73 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42740.1793 | 71234.0591 | 73607.8019 | 73607.8019 | 66484.0116 | 83105.3348 | 142466.8373 | 147215.6037 | 142466.8373 | 147215.6037 | 147215.6037 | 246942.2617 | 294431.2075 | 284933.6745 | 294431.2075 | 294431.2075 | 360916.5001 | 662471.4978 | 641101.4082 | 662471.4978 | 641101.4082 | 662471.4978 | 886856.158 | 890418.6936 | 920098.8043 | 890418.6936 | 920098.8043 | 884482.4153 | 764571.8985 | 846491.0025 | 819184.6345 | 846491.0025 | 819184.6345 | 441648.0922 | 441648.0922 | 427400.5118 | 441648.0922 | 427400.5118 | 283746.1626 | 184019.5047 | 172146.948 | 184019.5047 | 178083.2263 | 162649.415 | 71234.0591 | 73607.8019 | 73607.8019 | 71234.0591 | 73607.8019 | 42740.1793 | 36803.9009 | 36803.9009 | 33242.6463 | 36803.9009 | 23747.842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -30561291.73
Carbon
540039.XXXXXXXXXX | Carbon | Tunnels Carbon | Tunnels Carbon | X | CON | TPRAI | C | C06 | TN | CT | PL | CAR | 540039.TN.CT.PL.CAR |  |  |  | 0 | 0 | 43800000.9965 | 43800000.9965 | 43800000.9965 | 0 | 43800001 | -0.003455 | -43800000.9965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14325.3333 | 2410756 | 8663865.0001 | 7466543.6665 | 7288069.3332 | 8038635.3333 | 8287191.3333 | 1630614.9968 | 0 | 0 | [56 empty] | 3581.3333 | 3581.3333 | 3581.3333 | 3581.3333 | 3581.3333 | 26395.3333 | 26395.3333 | 26395.3333 | 26395.3333 | 26395.3333 | 26395.3333 | 346314.6667 | 346314.6667 | 346314.6667 | 604929.3333 | 604929.3333 | 604929.3333 | 716090 | 716090 | 716090 | 747177.6667 | 747177.6667 | 747177.6667 | 709336.6667 | 709336.6667 | 709336.6667 | 770561.3333 | 770561.3333 | 770561.3333 | 748903.3333 | 748903.3333 | 748903.3333 | 650835 | 650835 | 650835 | 488797.3333 | 488797.3333 | 488797.3333 | 515187.6667 | 515187.6667 | 515187.6667 | 589114 | 589114 | 589114 | 618745.3333 | 618745.3333 | 618745.3333 | 644303 | 644303 | 644303 | 608197.3333 | 608197.3333 | 608197.3333 | 650311 | 650311 | 650311 | 582032 | 582032 | 582032 | 706659 | 706659 | 706659 | 806716 | 806716 | 806716 | 803869 | 803869 | 803869 | 634482.3333 | 634482.3333 | 634482.3333 | 519058 | 519058 | 519058 | 804123.6667 | 804123.6667 | 804123.6667 | 186485.6667 | 186485.6667 | 186485.6667 | 49304 | 49304 | 49304 | 36007 | 36007 | 36007 | 11101.33 | 0
NR VAT
540039.6.9999999.C14R00.R11000 | NR VAT | Tunnels - NR VAT on Inflation | Tunnels - NR VAT on Inflation | F | CON | NRVAT | C | C14 | TN | CT | PL | VAT | 540039.TN.CT.PL.VAT | Sinisa Galac |  | VAT | 65724.0989 | 160516.448 | 62548078.6469 | 62708595.0948 | 62708595.0947 | 0.00011255 |  | 62708595.0948 | -27381659.4348 | 35326935.66 | 67432357.25 | 35166419.212 | 31281.6156 | 33550.2692 | -2268.6536 | 535712.4272 | 535710.4943 | 1.9329 | 0 | 0 | 94792.349 | 535712.4272 | 634617.6314 | 190027.8664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61253444.8209 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94792.349 | 34442.4833 | 31281.6156 | 40287.3833 | 35035.2764 | 39928.8964 | 38368.8296 | 46688.9081 | 47991.4017 | 47606.034 | 65957.8074 | 51600.365 | 56523.4264 | 35936.5109 | 33265.8265 | 23726.2783 | 45237.3702 | 46480.0134 | 48864.3298 | 64026.396 | 67067.658 | 69422.4547 | 69321.9688 | 64276.5761 | 66992.2487 | 51868.7043 | 46385.8106 | 45638.0776 | 46135.2738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61253444.8209
540039.6.XXXXX03.C080NR.D1Y100 | NR VAT | Tunnels - Advanced Works NR VAT | Tunnels - Advanced Works NR VAT | V | EEW | NRVAT | C | C08 | TN | CT | PL | VAT | 540039.TN.CT.PL.VAT | Sinisa Galac | Sinisa Galac | VAT | 1243.104 | 849075.4801 | 9937275.5277 | 10786351.0078 | 10786351.0078 | 0 | 340694377.2683 | -329908026.2605 | 353175492.8622 | 363961843.87 | 317549673.76 | 363112768.3899 | 676.752 | 676.752 | 0 | 66161.3432 | 66161.3432 | 0 | 2157637.7 | -1335274.51 | 25469.1861 | 66161.3432 | 662.4 | 14462.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9857232.4886 | 9865.28 | 7524.72 | -128.1 | 2389.96 | 2700.96 | 4518.37 | 3291.65 | -1366375.72 | 1779.34 | 1491.15 | 2520.11 | -4852.23 | 2565.63 | 1876.61 | -14255.02 | -237.71 | 2974.37 | -7408.72 | -921.21 | 1916.13 | 2234.21 | 39264.18 | -3216.0359 | 676.752 | 566.352 | 676.752 | 14409.2774 | 14519.6774 | 33889.7598 | 676.752 | 566.352 | 635.6206 | 0 | 110.4 | 0 | 110.4 | 0 | 110.4 | 0 | 110.4 | 0 | 110.4 | 0 | 110.4 | 0 | 110.4 | 0 | 110.4 | 0 | 110.4 | 0 | 110.4 | 6900 | 7010.4 | 0 | 110.4 | 0 | 110.4 | 0 | 110.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9857232.4886
540039.6.XXXXX04.C080NR.D1Y100 | NR VAT | Tunnels - Construction NR VAT | Tunnels - Construction NR VAT | V | CON | NRVAT | C | C08 | TN | CT | PL | VAT | 540039.TN.CT.PL.VAT | Sinisa Galac | Sinisa Galac | VAT | 624659.76 | 1193019.589 | 259717833.6428 | 260910853.2318 | 260910853.2318 | 0 |  | 260910853.2318 | -260874053.2318 | 36800 | 0 | -1156219.589 | 297309.04 | 317820.256 | -20511.216 | 5216503.0768 | 5216503.0768 | 0 | 0 | 0 | 568359.829 | 5216503.0768 | 5841660.3236 | 29404254.2336 | 55333841.6915 | 38152956.2502 | 37777965.7991 | 41820790.4281 | 41893432.1328 | 8326910.6924 | 2202976.4531 | 0 | -5628797.6783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368176.0567 | 200183.7723 | 327350.72 | 297309.04 | 381011.376 | 330794.096 | 376376.784 | 361074.976 | 438647.72 | 450141.3536 | 629790.4896 | 616621.0208 | 481601.9183 | 525783.5825 | 334301.2355 | 308946.8064 | 219987.6659 | 418744.7544 | 429538.003 | 450827.723 | 589740.6215 | 616734.7886 | 637336.2056 | 635364.3347 | 588149.8592 | 611988.3257 | 396770.3373 | 435257.2607 | 427763.9037 | 431591.977 | 863404.7612 | 881754.4663 | 3105213.1184 | 3103465.5723 | 3105213.1184 | 5524622.337 | 5536855.6308 | 5592341.7504 | 5619875.2956 | 5633028.3425 | 5629096.246 | 3996210.7222 | 4482164.1669 | 4038153.0062 | 6322025.7296 | 3745435.9377 | 3750897.078 | 4048669.7073 | 4026606.1723 | 4041679.2874 | 3944469.253 | 3949493.6247 | 3944469.253 | 3387511.0541 | 3832177.7213 | 3384889.4993 | 2582080.9453 | 2579459.3905 | 2553026.9902 | 2665854.3564 | 2663669.806 | 2665854.3564 | 3001106.0858 | 2998266.2645 | 2981445.839 | 3129168.3956 | 3573835.0628 | 3128731.6269 | 3256207.0256 | 3250527.383 | 3249435.1078 | 3069966.093 | 3069310.8221 | 3069966.093 | 3276895.3596 | 3272525.7567 | 3272525.7567 | 2933136.9662 | 3377803.6335 | 2933136.9662 | 3552610.8245 | 3552610.8245 | 3552610.8245 | 4032311.1719 | 4032311.1719 | 4032311.1719 | 4018159.524 | 4018159.524 | 4018159.524 | 3176200.7104 | 3620867.3776 | 3176200.7104 | 2602469.4762 | 2602469.4762 | 2602469.4762 | 4019425.4446 | 4019425.4446 | 4019425.4446 | 1685374.2221 | 949374.2662 | 949374.2662 | 1187494.4423 | 712161.1096 | 267494.4423 | 201399.4737 | 201399.4737 | 201399.4737 | 1200230.2368 | 385604.643 | 385604.643 | 385604.643 | 363474.362 | 363474.362 | 363474.362 | 363474.362 | 363474.362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5628797.6783
[17 empty] | 4450469.1528 | 17824449.6296 | 2730288944.3714 | 2748113394.0011 | 2748113394.0004 | 0.00072433 | 2754401971.9117 | -6288577.9107 | 183608699.1689 | 2931722093.17 | 3014301046.71 | 2913897643.5404 | 2118764.1882 | 2265347.697 | -146583.5088 | 37439990.1467 | 37439977.7091 | 12.4375 | 7231986.2527 | -499473.6646 | 6641467.8888 | 37439990.1467 | 41677703.154 | 270898620.1037 | 513788014.2895 | 376954485.2674 | 386560211.6941 | 436797138.4601 | 444093420.4267 | 84294184.5944 | 29784970.0931 | 0 | 112450675.2945 | 274339.27 | 209129.5873 | -35066.75 | 186029.93 | 163932.15 | 133068.41 | 120173.0112 | -1380288.79 | 60567.34 | 46938.15 | 58085.778 | -336381.7512 | 29834.7115 | 22637.4685 | 7892.2733 | -45740.5396 | 122434.8822 | -377753.135 | -163124.58 | 66012.63 | 63730.71 | 1809707.17 | 2557212.5746 | 2548623.7233 | 2331704.9646 | 4118764.1882 | 2803686.4966 | 2447463.4506 | 2896909.7889 | 2574688.8053 | 3126680.0461 | 3209466.0714 | 4358899.3692 | 4392956.7727 | 3431040.7794 | 3747729.4135 | 2382399.4115 | 2202774.2991 | 1568246.2498 | 2986334.506 | 3063072.4538 | 3216120.1314 | 4206848.6346 | 4400830.4912 | 4547838.3358 | 4535213.5703 | 4198222.279 | 4369802.7915 | 2886894.7031 | 3099978.8585 | 3046238.8362 | 3074781.4051 | 7955846.5411 | 8074633.3042 | 28695452.6302 | 28684917.9512 | 28699033.9635 | 52055691.3401 | 52133699.5266 | 52491451.0439 | 52663453.3483 | 52770904.3457 | 52745602.1595 | 37777330.804 | 40904335.5789 | 38047220.2838 | 53128348.0371 | 35107808.0026 | 35142949.2537 | 38389929.6758 | 38506570.2905 | 38603562.5096 | 38219843.9494 | 38363335.3558 | 38331004.6161 | 33584039.0388 | 36476460.0428 | 33598257.5703 | 25886036.748 | 25831326.6128 | 25661239.8634 | 26964849.748 | 27012017.3075 | 27026074.4146 | 30593453.9074 | 30553522.2749 | 30445286.4935 | 32270573.8024 | 35033838.8063 | 32169694.9577 | 33562809.7775 | 33364224.8456 | 33357196.2921 | 31720348.7985 | 31742522.6064 | 31746739.1319 | 34018989.4751 | 34064798.3635 | 34064798.3635 | 30997084.4498 | 33888049.1204 | 31026715.7831 | 37459969.9147 | 37485527.5814 | 37485527.5814 | 42125963.0536 | 42089857.3869 | 42089857.3869 | 42164617.7355 | 42206731.4022 | 42206731.4022 | 33869345.4381 | 36662399.7754 | 33801066.4381 | 27849102.0242 | 27973729.0242 | 27973729.0242 | 43061951.3876 | 43162008.3876 | 43162008.3876 | 15529067.4676 | 10790220.782 | 10790220.782 | 9575127.6607 | 6347074.3313 | 3485740.994 | 2840046.1329 | 2724621.7996 | 2724621.7996 | 10172290.5325 | 4657576.1561 | 4657576.1561 | 5036514.6698 | 4276473.1229 | 4276473.1229 | 4324066.0088 | 4186884.3421 | 4186884.3421 | 600581.0587 | 587284.0587 | 587284.0587 | 594479.3261 | 569573.6561 | 558472.3261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112450675.2945
1876.61
-14255.02
-237.71
2974.37
-7408.72
-921.21
1916.13
2234.21
39264.18

## ABP
Control Account | Account | Supplier | Description in PRISM | Contract | NEW PHASE | CONTRACTS AND GROUPS | PILLAR | Sub Pillar | PBS_01 | PBS_02 | PBS_03 | PBS_04 | PBS Control Account ID | Project Sheet Lead/ Budget Holder | Commercial Lead/PM/ Responsible Person | NR VAT | YTD Actuals | ACWP cumulative to date | ETC | EAC (Current) | EAC (Previous) | EAC Current vs EAC Previous (Variance) | WMS Baseline | EAC Current vs WMS Baseline (Variance) | CURRENT BUDGET VS EAC (Variance) | CURRENT BUDGET | BASELINE | REMAINING BUDGET | In Month Actuals | In Month Forecast | In Month Variance | FY FORECAST | FY FORECAST (Previous) | FY FORECAST (Variance) | Prior Years cumulative to Mar-22 | 2022/23 | 2023/24 | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | 2031/32 | 2032/33 | 2033/34 | 2034/35 | 2035/36 | Apr-22 | May-22 | Jun-22 | Jul-22 | Aug-22 | Sep-22 | Oct-22 | Nov-22 | Dec-22 | Jan-23 | Feb-23 | Mar-23 | Apr-23 | May-23 | Jun-23 | Jul-23 | Aug-23 | Sep-23 | Oct-23 | Nov-23 | Dec-23 | Jan-24 | Feb-24 | Mar-24 | Apr-24 | May-24 | Jun-24 | Jul-24 | Aug-24 | Sep-24 | Oct-24 | Nov-24 | Dec-24 | Jan-25 | Feb-25 | Mar-25 | Apr-25 | May-25 | Jun-25 | Jul-25 | Aug-25 | Sep-25 | Oct-25 | Nov-25 | Dec-25 | Jan-26 | Feb-26 | Mar-26 | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27 | Apr-27 | May-27 | Jun-27 | Jul-27 | Aug-27 | Sep-27 | Oct-27 | Nov-27 | Dec-27 | Jan-28 | Feb-28 | Mar-28 | Apr-28 | May-28 | Jun-28 | Jul-28 | Aug-28 | Sep-28 | Oct-28 | Nov-28 | Dec-28 | Jan-29 | Feb-29 | Mar-29 | Apr-29 | May-29 | Jun-29 | Jul-29 | Aug-29 | Sep-29 | Oct-29 | Nov-29 | Dec-29 | Jan-30 | Feb-30 | Mar-30 | Apr-30 | May-30 | Jun-30 | Jul-30 | Aug-30 | Sep-30 | Oct-30 | Nov-30 | Dec-30 | Jan-31 | Feb-31 | Mar-31 | Apr-31 | May-31 | Jun-31 | Jul-31 | Aug-31 | Sep-31 | Oct-31 | Nov-31 | Dec-31 | Jan-32 | Feb-32 | Mar-32 | Apr-32 | May-32 | Jun-32 | Jul-32 | Aug-32 | Sep-32 | Oct-32 | Nov-32 | Dec-32 | Jan-33 | Feb-33 | Mar-33 | Apr-33 | May-33 | Jun-33 | Jul-33 | Aug-33 | Sep-33 | Oct-33 | Nov-33 | Dec-33 | Jan-34 | Feb-34 | Mar-34 | Apr-34 | May-34 | Jun-34 | Jul-34 | Aug-34 | Sep-34 | Oct-34 | Nov-34 | Dec-34 | Jan-35 | Feb-35 | Mar-35 | Apr-35 | May-35 | Jun-35 | Jul-35 | Aug-35 | Sep-35 | Oct-35 | Nov-35 | Dec-35 | Jan-36 | Feb-36 | Mar-36
Other Client Scope
540039.6.4097130.CEC100.540100 | Other Client Scope | CASCADE | Cascade - Error Correction 4097130 | C | EEW | CASC1 | C | CC0 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | David Tooze; Adam Buckingham; Eve Herrington | REC | 0 | 3730.04 | 0 | 3730.04 | 3730.04 | 0 |  | 3730.04 | 0 | 3730.04 | 3730.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3730.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.4097130.C01000.540100 | Other Client Scope | CASCADE | Statutory Procedures & Powers - COWI A/S ARCADIS CH2M JV - Pre-application | C | EEW | CASC1 | C | CC0 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | David Tooze; Adam Buckingham; Eve Herrington | REC | 0 | 9113.73 | 0 | 9113.73 | 9113.73 | 0 |  | 9113.73 | 0 | 9113.73 | 9113.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9113.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.4097130.C01000.540300 | Other Client Scope | CASCADE | Statutory Procedures & Powers - COWI A/S ARCADIS CH2M JV - July accounts to be updated | C | EEW | CASC1 | C | CC0 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | David Tooze; Adam Buckingham; Eve Herrington | REC | 0 | 2024.57 | 0 | 2024.57 | 2024.57 | 0 |  | 2024.57 | 0 | 2024.57 | 2024.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.4097130.C02000.210100 | Other Client Scope | CASCADE | Statutory Procedures & Powers - COWI A/S ARCADIS CH2M JV - July accounts to be updated | C | EEW | CASC1 | C | CC0 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | David Tooze; Adam Buckingham; Eve Herrington | REC | 0 | 28981.08 | 0 | 28981.08 | 28981.08 | 0 |  | 28981.08 | 0 | 28981.08 | 28981.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28981.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.4097130.C03000.210100 | Other Client Scope | CASCADE | Statutory Procedures & Powers - COWI A/S ARCADIS CH2M JV - Project Management | C | EEW | CASC1 | C | CC0 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | David Tooze; Adam Buckingham; Eve Herrington | REC | 0 | 702338.35 | 0 | 702338.35 | 702338.35 | 0 |  | 702338.35 | 0 | 702338.35 | 702338.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 702338.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.4097130.C03000.430100 | Other Client Scope | CASCADE | Statutory Procedures & Powers - COWI A/S ARCADIS CH2M JV - Environmental | C | EEW | CASC1 | C | CC0 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | David Tooze; Adam Buckingham; Eve Herrington | REC | 0 | 560.01 | 0 | 560.01 | 560.01 | 0 |  | 560.01 | 0 | 560.01 | 560.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 560.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.4097130.C03000.630100 | Other Client Scope | CASCADE | Statutory Procedures & Powers - COWI A/S ARCADIS CH2M JV - Ground Investigation | C | EEW | CASC1 | C | CC0 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | David Tooze; Adam Buckingham; Eve Herrington | REC | 0 | 2362899.72 | 0 | 2362899.72 | 2362899.72 | 0 |  | 2362899.72 | 0 | 2362899.72 | 2362899.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2362899.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.4097130.C03100.630100 | Other Client Scope | CASCADE | Statutory Procedures & Powers - COWI A/S ARCADIS CH2M JV - Ground Investigation | C | EEW | CASC1 | C | CC0 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | David Tooze; Adam Buckingham; Eve Herrington | REC | 0 | 9299.57 | 0 | 9299.57 | 9299.57 | 0 |  | 9299.57 | 0 | 9299.57 | 9299.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9299.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.4097130.C04000.540100 | Other Client Scope | CASCADE | Statutory Procedures & Powers - COWI A/S ARCADIS CH2M JV - Pre-application | C | EEW | CASC1 | C | CC0 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | David Tooze; Adam Buckingham; Eve Herrington | REC | 0 | 144648.5 | 0 | 144648.5 | 144648.5 | 0 |  | 144648.5 | 0 | 144648.5 | 144648.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144648.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.4097130.C05000.210100 | Other Client Scope | CASCADE | Statutory Procedures & Powers - COWI A/S ARCADIS CH2M JV - Project Management | C | EEW | CASC1 | C | CC0 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | David Tooze; Adam Buckingham; Eve Herrington | REC | 0 | 214695.82 | 0 | 214695.82 | 214695.82 | 0 |  | 214695.82 | 0 | 214695.82 | 214695.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 214695.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.4097130.C09000.210100 | Other Client Scope | CASCADE | Statutory Procedures & Powers - COWI A/S ARCADIS CH2M JV - Project Management | C | EEW | CASC1 | C | CC0 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | David Tooze; Adam Buckingham; Eve Herrington | REC | 0 | 86208.61 | 0 | 86208.61 | 86208.61 | 0 |  | 86208.61 | 0 | 86208.61 | 86208.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86208.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.4097130.C09000.630100 | Other Client Scope | CASCADE | Statutory Procedures & Powers - COWI A/S ARCADIS CH2M JV - Ground Investigation | C | EEW | CASC1 | C | CC0 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | David Tooze; Adam Buckingham; Eve Herrington | REC | 0 | 672.97 | 0 | 672.97 | 672.97 | 0 |  | 672.97 | 0 | 672.97 | 672.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 672.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.4097130.C09500.210100 | Other Client Scope | CASCADE | Statutory Procedures & Powers - COWI A/S ARCADIS CH2M JV - Project Management | C | EEW | CASC1 | C | CC0 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | David Tooze; Adam Buckingham; Eve Herrington | REC | 0 | 10474.14 | 0 | 10474.14 | 10474.14 | 0 |  | 10474.14 | 0 | 10474.14 | 10474.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10474.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.4097130.C48100.210100 | Other Client Scope | CASCADE | TO 48 - EW & GI - Enabling Works Delivery | C | EEW | CASC1 | C | CC3 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | David Tooze; Adam Buckingham; Eve Herrington | REC | 0 | 44816.265 | 0 | 44816.265 | 44816.265 | 0 |  | 44816.265 | 0.005 | 44816.27 | 44816.26 | 0.005 | 0 | 0 | 0 | 0 | 0 | 0 | 44816.265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.4097130.C48200.210300 | Other Client Scope | CASCADE | TO 48 - EW & GI - EW/GI Cost Estimating & Planning | C | EEW | CASC1 | C | CC3 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | David Tooze; Adam Buckingham; Eve Herrington | REC | 0 | 8.29 | 0 | 8.29 | 8.29 | 0 |  | 8.29 | 0 | 8.29 | 8.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.4097130.C48500.210100 | Other Client Scope | CASCADE | TO 48 - EW & GI - HE Enabling Works Delivery | C | EEW | CASC1 | C | CC3 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | David Tooze; Adam Buckingham; Eve Herrington | REC | 0 | 39367.58 | 0 | 39367.58 | 39367.58 | 0 |  | 39367.58 | 0 | 39367.58 | 39367.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39367.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.4097130.C48800.210100 | Other Client Scope | CASCADE | TO 48 - EW & GI - Project Controls | C | EEW | CASC1 | C | CC3 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | David Tooze; Adam Buckingham; Eve Herrington | REC | 0 | 2292.19 | 0 | 2292.19 | 2292.19 | 0 |  | 2292.19 | 0 | 2292.19 | 2292.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2292.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.9999999.C0R800.210100 | Other Client Scope | Cascade Uninstructed Adv Works | Cascade Uninstructed Works Advanced Works | F | EEW | CASC1 | C | CC0 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | David Tooze; Adam Buckingham; Eve Herrington | REC | 0 | 0 | 7098159.7694 | 7098159.7694 | 7098159.7694 | 0 | 21641885.5408 | -14543725.7714 | -7098159.7694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7098159.7694 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7098159.7694
540039.6.4101290.C00000.210100 | Other Client Scope | MOTT MACDONALD | Construction, Commissioning & H/O - MOTT MACDONALD GROUP LTD - Project Management | X | EEW | COMMO | C | CS1 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | David Carpenter | HYB | 0 | 412123.75 | 0 | 412123.75 | 412123.75 | 0 |  | 412123.75 | 0 | 412123.75 | 412123.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 412123.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.0000000.C00000.210100 | Other Client Scope | A-ONE + INTEGRATED | Construction, Commissioning & H/O - A-ONE + INTEGRATED HIGHWAY SERVICES (CIS) | X | EEW | HEPOS | C | C03 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | Closed Account | REC | 0 | 15647.52 | 0 | 15647.52 | 15647.52 | 0 |  | 15647.52 | 0 | 15647.52 | 15647.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15647.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.9999999.C09600 | Other Client Scope | Gravesend Ferry | Gravesend Ferry | F | EEW | HEPOS | C | CS1 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac |  | REC | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.4105142.C000M3.210100 | Other Client Scope | Osborne Clarke LLP | Construction, Commissioning & H/O - Osborne Clarke LLP - Project Management | X | EEW | HEPOS | C | C03 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac |  | REC | 0 | 1285.2 | 0 | 1285.2 | 1285.2 | 0 |  | 1285.2 | 0 | 1285.2 | 1285.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1285.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.9999999.C07100 | Other Client Scope | ITS | ITS | F | CON | ITSIT | C | C07 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac |  | HYB | 0 | 0 | 9501588.0129 | 9501588.0129 | 9501588.0129 | 0 |  | 9501588.0129 | 380385.8271 | 9881973.84 | 9501588.07 | 9881973.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 771753.4567 | 1393165.331 | 1443279.1918 | 1443279.1918 | 1443279.1918 | 1443279.1918 | 1443279.1918 | 120273.266 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70159.4052 | 70159.4052 | 70159.4052 | 70159.4052 | 70159.4052 | 70159.4052 | 70159.4052 | 70159.4052 | 70159.4052 | 70159.4052 | 70159.4052 | 70159.4052 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 120273.266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.9999999.C03000 | Other Client Scope | Cost Items for which there are no agreements / control accounts | Cost items for which there are no agreements / control accounts | X | EEW | TPPSS | C | C03 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac |  | HYB | 0 | 1.4552e-11 | 0 | 1.4552e-11 | 1.4552e-11 | 0 |  | 1.4552e-11 | -1.4552e-11 | 0 | 0 | -1.4552e-11 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4552e-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.9999999.C03700 | Other Client Scope | Ingrebourne Valley Limited | Ingebourne Valley Limited | X | EEW | TPOTH | C | CL1 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | Natasha Juckes; Matt Page | HYB | 0 | 2.9104e-10 | 0 | 2.9104e-10 | 2.9104e-10 | 0 |  | 2.9104e-10 | -2.9104e-10 | 0 | 0 | -2.9104e-10 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9104e-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.XXXXXXX.C00100.D1Y046 | Other Client Scope | NORTHUMBRIAN WATER | Northumbrian Water | C | EEW | STATS | C | C03 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | Warren Pavett/Shauna Dellar | HYB | 0 | 162642.0004 | 75000 | 237642.0004 | 237642.0004 | 0 |  | 237642.0004 | -85000.0004 | 152642 | 188805.49 | -10000.0004 | 0 | 0 | 0 | 12000 | 12000 | 0 | 150642.0004 | 0 | 12000 | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37500 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.4105716.C002M3.D1Y046 | Other Client Scope | SOUTHERN WATER | Southern Water - Advanced Construction Works | C | EEW | STATS | C | C03 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | Warren Pavett/Shauna Dellar | HYB | 0 | 2750 | 0 | 2750 | 2750 | 0 |  | 2750 | 0 | 2750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.4103431.CEC1M3.D1Y041 | Other Client Scope | UK POWER NETWORKS | UK Power Networks - Error Correction 4103431 | X | EEW | STATS | C | C03 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | Warren Pavett/Shauna Dellar | HYB | 0 | 2.9104e-11 | 0 | 2.9104e-11 | 2.9104e-11 | 0 |  | 2.9104e-11 | -2.9104e-11 | 0 | 0 | -2.9104e-11 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9104e-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.4106851.C000M3.D1Y041 | Other Client Scope | UK POWER NETWORKS | Construction, Commissioning & H/O - UK POWER NETWORKS (OPERATIONS) LTD (CIS) DIVERT/CONNECT - Utilit | X | EEW | STATS | C | C03 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | Warren Pavett/Shauna Dellar | HYB | 0 | 0.0018877 | 0 | 0.0018877 | 0.0018877 | 0 |  | 0.0018877 | -0.0018877 | 0 | 496983.21 | -0.0018877 | 0 | 0 | 0 | 0 | 0 | 0 | 86788.3419 | -86788.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | -86788.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.4107471.C000M3.210100 | Other Client Scope | INGREBOURNE VALLEY LTD | Construction, Commissioning & H/O - INGREBOURNE VALLEY LTD - Project Management | C | EEW | TPOTH | C | CL1 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | Natasha Juckes; Matt Page | HYB | 181105.4772 | 286555.794 | 331572.0572 | 618127.8512 | 618127.8512 | 0 |  | 618127.8512 | -278469.3212 | 339658.53 | 85000 | 53102.736 | 0 | 0 | 0 | 12674.5009 | 12674.5009 | 0 | 113861.625 | 160019.6681 | 12674.5009 | 331572.0572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97000 | 84100 | -159450.65 | 50000 | 46410.75 | 49886.79 | 31975.3612 | -50332.07 | 0 | 0 | 4565.668 | 5863.8188 | 21669.0815 | 15160.8585 | 28947.2933 | -53102.8296 | 111860.5122 | 113839.455 | -225699.87 | 0 | 0 | 0 | 0 | 0 | 0 | 181105.4772 | 75233.29 | 75233.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.4.XXXXXXX.C10000.220300 | Other Client Scope |  | Development Phase (excl. ECI) - PCF Stage 4: Surveys (GI, ATT, UTT) |  |  | TPOTH | C | CC0 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 2806319.01 | 2806319.01 | 12302517.86 | 2806319.01 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.4.XXXXXXX.C20000.220300 | Other Client Scope |  | Development Phase (excl. ECI) - PCF Stage 4: SU & NRTS design |  |  | TPOTH | C | CC0 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 3205949.7 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.5.XXXXXXX.C10000.220300 | Other Client Scope |  | Development Phase (excl. ECI) - PCF Stage 5: Surveys (GI, ATT, UTT) |  |  | TPOTH | C | CC0 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 633236.13 | 633236.13 | 0 | 633236.13 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.5.XXXXXXX.C20000.220300 | Other Client Scope |  | Development Phase (excl. ECI) - PCF Stage 5: SU & NRTS design |  |  | TPOTH | C | CC0 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 2014421.61 | 2014421.61 | 5023496.24 | 2014421.61 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.4098871.CEC100.D1Y044 | Other Client Scope | HS1 LIMITED | HS1 - Error Correction 4098871 | X | EEW | TPRAI | C | C03 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | Bob Jheeta / Warren Pavett | HYB | 0 | 2430 | 0 | 2430 | 2430 | 0 |  | 2430 | 0 | 2430 | 2430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.4100145.CEC100.D1Y044 | Other Client Scope | NETWORK RAIL | Network Rail - Error Correction 4100145 | C | EEW | TPRAI | C | C03 | TN | CT | PL | OCS | 540039.TN.CT.PL.OCS | Sinisa Galac | Bob Jheeta / Warren Pavett | HYB | 0 | 67521.5438 | 22478.4562 | 90000 | 90000 | 0 |  | 90000 | -45000 | 45000 | 20000 | -22521.5438 | 5000 | 5000 | 0 | 37521.5438 | 37521.5438 | 0 | 60000 | -30000 | 37521.5438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22478.4562 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 6000 | 6000 | 6000 | -48000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | -17478.4562 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22478.4562
Inflation
540039.6.9999999.C09200.C3X020 | Project Inflation | Tunnels Inflation on Base | Tunnels Inflation on Base | F | CON | INFLA | C | C09 | TN | CT | PL | IN2 | 540039.TN.CT.PL.IN2 | Sinisa Galac |  | INCL. | 281264.9231 | 528596.391 | 738244364.5035 | 738772960.8945 | 738772960.8945 | 0 |  | 738772960.8945 | -233761622.5845 | 505011338.31 | 546871114.82 | 504482741.919 | 187679.221 | 187679.221 | 0 | 528596.391 | 528596.391 | 0 | 0 | 0 | 528596.391 | 2141801.4413 | 2712752.3539 | 62975517.341 | 123694930.1183 | 101593862.5587 | 114310650.406 | 136195974.2004 | 142134851.1718 | 19469654.4596 | 13978680.5284 | 0 | 19035689.9241 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132142.99 | 208774.18 | 187679.221 | 138568.5158 | 142696.4073 | 168425.5154 | 121092.3668 | 147664.2604 | 148552.4193 | 147783.6545 | 200632.9503 | 199021.8813 | 275743.342 | 215720.5893 | 235899.539 | 191581.4003 | 172201.9296 | 132375.5934 | 222359.7157 | 227609.6115 | 205641.9181 | 195847.6043 | 208443.2915 | 218168.9448 | 366181.6603 | 280484.05 | 291856.6343 | 166124.3673 | 109437.2042 | 63860.2292 | 40175.4154 | 1808254.5665 | 1808254.5665 | 6688195.4647 | 6688195.4647 | 6688195.4647 | 12971608.1992 | 12971608.1992 | 12971608.1992 | 13127162.4025 | 13127162.4025 | 13127162.4025 | 9801490.9059 | 9801490.9059 | 9801490.9059 | 8576003.4658 | 8576003.4658 | 8576003.4658 | 9726986.5985 | 9726986.5985 | 9726986.5985 | 10032430.6943 | 10032430.6943 | 10032430.6943 | 9157521.5699 | 9157521.5699 | 9157521.5699 | 7087310.2524 | 7087310.2524 | 7087310.2524 | 7587358.3364 | 7587358.3364 | 7587358.3364 | 8780249.7456 | 8780249.7456 | 8780249.7456 | 9567910.0024 | 9567910.0024 | 9567910.0024 | 10065652.4582 | 10065652.4582 | 10065652.4582 | 9689737.9292 | 9689737.9292 | 9689737.9292 | 10506702.0062 | 10506702.0062 | 10506702.0062 | 9823502.8458 | 9823502.8458 | 9823502.8458 | 11904390.029 | 11904390.029 | 11904390.029 | 13164063.1857 | 13164063.1857 | 13164063.1857 | 13338251.724 | 13338251.724 | 13338251.724 | 10916391.7561 | 10916391.7561 | 10916391.7561 | 8995410.777 | 8995410.777 | 8995410.777 | 14128229.4668 | 14128229.4668 | 14128229.4668 | 3329189.0277 | 3329189.0277 | 3329189.0277 | 984921.4901 | 984921.4901 | 984921.4901 | 803603.8631 | 803603.8631 | 803603.8631 | 1372170.439 | 1372170.439 | 1372170.439 | 1751108.9527 | 1751108.9527 | 1751108.9527 | 1798701.8386 | 1798701.8386 | 1798701.8386 | 551277.0587 | 551277.0587 | 551277.0587 | 558472.3261 | 558472.3261 | 558472.3261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19035689.9241
540039.6.9999999.C09600.C3X020 | Project Inflation | Tunnels Inflation on Risk | Tunnels Inflation on Risk | F | CON | INFLA | C | C09 | TN | CT | PL | IN2 | 540039.TN.CT.PL.IN2 | Sinisa Galac |  | INCL. | 0 | 0 | 0 | 0 | 0 | 0 | 738772960.8917 | -738772960.8917 | 59196049.86 | 59196049.86 | 144423893.38 | 59196049.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.9999999.C01X00 | Project Inflation | Finance/ Programme Overlay | Tunnels Overlay | F | EEW | OVER1 | C | C24 | TN | CT | PL | IN2 | 540039.TN.CT.PL.IN2 | Paul Williamson |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Main Works - Fee
540039.6.TUN.FEE | Contractor Fee | Tunnels Fee | Tunnels Fee | F | CON | MWSTU | C | C04 | TN | DP | P2 | FEE | 540039.TN.DP.P2.FEE |  |  |  | 0 | 0 | 143770109.2267 | 143770109.2267 | 143770109.2267 | 0 | 143770109.2292 | -0.00252 | -143770109.2267 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 17762540.4722 | 31621085.9824 | 21190778.3594 | 21690020.3058 | 24205399.9979 | 24344805.4151 | 2955478.6939 | 0 | 0 | 0 | [26 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 547370.0329 | 547370.0329 | 2025885.7949 | 2025885.7949 | 2025885.7949 | 3530047.6739 | 3530047.6739 | 3530047.6739 | 3370033.7975 | 3370033.7975 | 3370033.7975 | 2234697.3092 | 2234697.3092 | 2234697.3092 | 3845088.0216 | 2084423.8363 | 2084423.8363 | 2264318.9894 | 2264318.9894 | 2264318.9894 | 2200681.7721 | 2200681.7721 | 2200681.7721 | 1912530.2515 | 1912530.2515 | 1912530.2515 | 1436419.2679 | 1436419.2679 | 1436419.2679 | 1513961.4949 | 1513961.4949 | 1513961.4949 | 1731177.5809 | 1731177.5809 | 1731177.5809 | 1818242.0953 | 1818242.0953 | 1818242.0953 | 1893337.9807 | 1893337.9807 | 1893337.9807 | 1787249.1118 | 1787249.1118 | 1787249.1118 | 1910990.5315 | 1910990.5315 | 1910990.5315 | 1710368.8648 | 1710368.8648 | 1710368.8648 | 2076556.2035 | 2076556.2035 | 2076556.2035 | 2370551.0661 | 2370551.0661 | 2370551.0661 | 2362185.6539 | 2362185.6539 | 2362185.6539 | 1864481.5892 | 1864481.5892 | 1864481.5892 | 1525333.9223 | 1525333.9223 | 1525333.9223 | 2362933.973 | 2362933.973 | 2362933.973 | 548145.7065 | 548145.7367 | 548145.7367 | 145068.5855 | 145068.5855 | 145068.5855 | 105998.1061 | 105998.1061 | 105998.1061 | 557841.4393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Main Works - Tunnels (Phase 1)
540039.5.9999999.C04700.820000 | Stage 1 Scope | MWC Detailed Design and ECI | Phase 1 - Mobilisation Phase | X | CON | MWSTU | C | C11 | TN | DP | P1 | PH1 | 540039.TN.DP.P1.PH1 | Sinisa Galac | Sinisa Galac/ Natasha Juckes | HYB | 3436552 | 5510449.04 | 54374025.32 | 59884474.36 | 59884474.36 | 0 | 59884474.36 | 0 | 1160154.77 | 61044629.13 | 28428936.57 | 55534180.09 | 1876792.21 | 1876792.21 | 0 | 5510449.04 | 5510449.04 | 0 | 0 | 0 | 5510449.04 | 26120727.2 | 24803230.01 | 3450068.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1632700 | 2000956.83 | 1876792.21 | 1709268 | 1727284 | 2070714 | 1486320 | 1809482 | 1817364 | 1804978 | 2446420.4 | 2422774.4 | 3351201.2 | 2617401.73 | 2857519.47 | 2308999.33 | 2071203.52 | 1587729.93 | 1874442.09 | 1933101.05 | 1665113.05 | 1496896.52 | 1615110.07 | 1724700.55 | 3483983.86 | 2464507.24 | 2577442.8 | 1716028.11 | 1037046 | 501070 | 195924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DP Risk
540039.6.9999999.C12R00.C3X010 | Risk Quota | RISK | TU- Contractor/Delivery Partner Risk- Construction- Threats | F | CON | MWSTU | C | C12 | TN | DP | P2 | RK4 | 540039.TN.DP.P2.RK4 | Sinisa Galac |  | HYB | 0 | 0 | 39780445 | 39780445 | 39780445 | 0 | 39780445 | 0 | 163923784.49 | 203704229.49 | 298877439.79 | 203704229.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2652489.28 | 8038258.29 | 6568445.67 | 6722762.97 | 7500274.89 | 7543365.6 | 754848.3 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25560.65 | 25560.65 | 316120.57 | 316120.57 | 316120.57 | 551002.09 | 551002.09 | 551002.09 | 651961.51 | 651961.51 | 651961.51 | 680196.21 | 680196.21 | 680196.21 | 645827.77 | 645827.77 | 645827.77 | 701433.94 | 701433.94 | 701433.94 | 681763.47 | 681763.47 | 681763.47 | 592694.91 | 592694.91 | 592694.91 | 445527.48 | 445527.48 | 445527.48 | 469496.03 | 469496.03 | 469496.03 | 536638.22 | 536638.22 | 536638.22 | 563550.14 | 563550.14 | 563550.14 | 586762.52 | 586762.52 | 586762.52 | 553970.11 | 553970.11 | 553970.11 | 592218.98 | 592218.98 | 592218.98 | 530206.18 | 530206.18 | 530206.18 | 643395.86 | 643395.86 | 643395.86 | 734270.61 | 734270.61 | 734270.61 | 731684.84 | 731684.84 | 731684.84 | 577842.92 | 577842.92 | 577842.92 | 473011.29 | 473011.29 | 473011.29 | 731916.15 | 731916.15 | 731916.15 | 170959.05 | 170959.29 | 170959.29 | 46366.85 | 46366.85 | 46366.85 | 34290.04 | 34290.04 | 34290.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DP Opportunities
540039.6.9999999.C12O00.C3X010 | Risk Quota | RISK | TU- Contractor/Delivery Partner Risk- Construction- Opportunities | F | CON | MWSTU | C | C12 | TN | DP | P2 | OP4 | 540039.TN.DP.P2.OP4 | Sinisa Galac |  | HYB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -11528401.95 | -11528401.95 | 0 | -11528401.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Risk
540039.6.9999999.C12R00.R11000 | Project Risk | RISK | TU- Employer Risk- Threats | F | CON | RSK01 | C | C12 | TN | CT | PL | RK3 | 540039.TN.CT.PL.RK3 | Sinisa Galac |  | HYB | 0 | 0 | 185105983.9862 | 185105983.9862 | 185105983.9862 | 0 | 185105983.9862 | 0 | -110391923.1662 | 74714060.82 | 8396602.39 | 74714060.82 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 111530.4027 | 11902250.0904 | 34179067.738 | 27794368.0731 | 28421648.6613 | 31296861.6067 | 30609009.1218 | 8938823.4433 | 11852424.8488 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9638.4299 | 9638.4299 | 9638.4299 | 13769.1855 | 13769.1855 | 13769.1855 | 13769.1855 | 13769.1855 | 13769.1855 | 98060.8767 | 98060.8767 | 98060.8767 | 98060.8767 | 98060.8767 | 98060.8767 | 1280062.2444 | 1280062.2444 | 1280062.2444 | 2491232.699 | 2491232.699 | 2491232.699 | 2904663.1747 | 2904663.1747 | 2904663.1747 | 3019522.2883 | 3019522.2883 | 3019522.2883 | 2621315.2651 | 2621315.2651 | 2621315.2651 | 2847521.8512 | 2847521.8512 | 2847521.8512 | 2863030.7427 | 2863030.7427 | 2863030.7427 | 2500537.3816 | 2500537.3816 | 2500537.3816 | 1901858.4339 | 1901858.4339 | 1901858.4339 | 1999362.7994 | 1999362.7994 | 1999362.7994 | 2272498.0596 | 2272498.0596 | 2272498.0596 | 2381976.088 | 2381976.088 | 2381976.088 | 2476404.3352 | 2476404.3352 | 2476404.3352 | 2343004.4044 | 2343004.4044 | 2343004.4044 | 2498601.283 | 2498601.283 | 2498601.283 | 2246332.4369 | 2246332.4369 | 2246332.4369 | 2706789.4684 | 2706789.4684 | 2706789.4684 | 2980564.0139 | 2980564.0139 | 2980564.0139 | 2970045.0442 | 2970045.0442 | 2970045.0442 | 2344214.1864 | 2344214.1864 | 2344214.1864 | 1917757.8027 | 1917757.8027 | 1917757.8027 | 2970986.0072 | 2970986.0072 | 2970986.0072 | 689006.4953 | 689006.4953 | 689006.4953 | 182162.8968 | 182162.8968 | 182162.8968 | 133034.2809 | 133034.2809 | 133034.2809 | 1975404.1415 | 1975404.1415 | 1975404.1415 | 1975404.1415 | 1975404.1415 | 1975404.1415 | 1975404.1415 | 1975404.1415 | 1975404.1415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.9999999.C12R06.R11000 | Project Risk | RISK | TU- Employer Risk- National Highways Stage 6 Fee Adj | F | CON | MWSTU | C | C12 | TN | CT | PL | RK3 | 540039.TN.CT.PL.RK3 | Sinisa Galac |  | HYB | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | -6593333.13 | -6593333.13 | 0 | -6593333.13 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Opportunities
540039.6.9999999.C12O00.R14000 | Project Opportunities | RISK | TU- Employer Risk- Opportunities | F | CON | RSK01 | C | C12 | TN | CT | PL | OP3 | 540039.TN.CT.PL.OP3 | Sinisa Galac |  | HYB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -104801218.02 | -104801218.02 | 0 | -104801218.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Incentives
540039.6.9999999.C16000.C3X060 | Incentives | Tunnels - Incentives | Tunnels - Incentives | F | CON | MWSTU | C | C16 | TN | DP | PL | INS | 540039.TN.DP.PL.INS | Sinisa Galac | Sinisa Galac/ Natasha Juckes | HYB | 0 | 0 | 24500000.02 | 24500000.02 | 24500000.02 | 0 | 24500000 | 0.02 | -24500000.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 2416666.67 | 2416666.67 | 2416666.67 | 2416666.67 | 2416666.67 | 11416666.67 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2416666.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2416666.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2416666.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2416666.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2416666.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 0 | 0 | 5000000 | 2416666.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Stats Undertakers (Utilities)
540039.6.4104809.C00000.D1Y046 | Utilities (Client) | ANGLIAN WATER | Anglian Water | F | EEW | STATS | C | C03 | TN | CT | PL | UTN | 540039.TN.CT.PL.UTN | Sinisa Galac | Warren Pavett/Shauna Dellar | HYB | 600 | 6000 | 10800 | 16800 | 16800 | 0 |  | 16800 | -14400 | 2400 | 0 | -3600 | 600 | 600 | 0 | 6000 | 6000 | 0 | 0 | 0 | 6000 | 3600 | 3600 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 600 | 1200 | 600 | 600 | 600 | 0 | 600 | 0 | 600 | 0 | 600 | 0 | 600 | 0 | 600 | 0 | 600 | 0 | 600 | 0 | 600 | 0 | 600 | 0 | 600 | 0 | 600 | 0 | 600 | 0 | 600 | 0 | 600 | 0 | 600 | 0 | 600 | 0 | 600 | 0 | 600 | 0 | 600 | 0 | 600 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.4101428.C000M3.D1Y045 | Utilities (Client) | BT OPENREACH early design | BT OPENREACH EARLY DESIGN - Utilities Telecoms | X | EEW | STATS | C | C03 | [5 empty] | Sinisa Galac | Warren Pavett/Shauna Dellar | HYB | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.4108361.C000M3.D1Y041 | Utilities (Client) | UK POWER NETWORKS | Construction, Commissioning & H/O - UK POWER NETWORKS (OPERATIONS) LTD (CIS) DIVERT/CONNECT - Utilit | C | EEW | STATS | C | C03 | TN | CT | PL | UTN | 540039.TN.CT.PL.UTN | Sinisa Galac | Warren Pavett/Shauna Dellar | HYB | 0 | 1021963.8277 | 53571915.6988 | 54593879.5265 | 54593879.5265 | 0 | 54610679.5265 | -16800 | -53449621.3265 | 1144258.2 | 0 | 122294.3723 | 0 | 0 | 0 | -137294.37 | -137294.37 | 0 | 569438.6804 | 589819.5173 | -137294.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53571915.6988 | 167473.99 | 117504.8673 | 124512 | 133639.97 | 114820.44 | 78663.25 | 84906 | 35669 | 52788 | 39447 | 45000 | -404605 | 0 | 0 | -15000 | 0 | 0 | -291783.87 | 56496.5 | 56496.5 | 56496.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53571915.6988
540039.6.4108361.C001M3.D1Y041 | Utilities (Client) | UK POWER NETWORKS | UK POWER NETWORKS | C | CON | STATS | C | C03 | TN | CT | PL | UTN | 540039.TN.CT.PL.UTN | Sinisa Galac | Warren Pavett/Shauna Dellar | HYB | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 200000 | 200000 | 0 | 200000 | 0 | 0 | 0 | -200000 | -200000 | 0 | 0 | 200000 | -200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | -200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.9999999.C09500 | Utilities (Client) | Utilites General | Utilities General | X | EEW | STATS | C | C03 | [5 empty] | Sinisa Galac | Future | HYB | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.5.XXXXXXX.C00100.D1Y046 | Utilities (Client) | Essex and Suffolk Water | Essex & Suffolk Water | U | EEW | STATS | C | C03 | [5 empty] | Sinisa Galac | Warren Pavett/Shauna Dellar | HYB | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.5.XXXXXXX.C00100.D1Y041 | Utilities (Client) | UK POWER NETWORKS | UKPN | U | EEW | STATS | C | C03 | [5 empty] | Sinisa Galac | Warren Pavett/Shauna Dellar | HYB | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Main Works
540039.6.9999999.C00000.C10153 | Stage 2 Unlet Works | Main Works Advanced Works | Main Works Advanced works | F | CON | MWSTU | C | C10 | TN | DP | P2 | P2U | 540039.TN.DP.P2.P2U | Sinisa Galac | Sinisa Galac/ Natasha Juckes | HYB | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 62687753.82 | 62687753.82 | 44603439.12 | 62687753.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.9999999.C05500.D1Y043 | Stage 2 Unlet Works | Construction TBA | TU - SU Contestable works | F | CON | MWSTU | C | C05 | TN | DP | P2 | P2U | 540039.TN.DP.P2.P2U | Sinisa Galac | Sinisa Galac/ Natasha Juckes | HYB | 0 | 0 | -30561291.73 | -30561291.73 | -30561291.73 | 0 |  | -30561291.73 | 48541461.73 | 17980170 | 28285.49 | 17980170 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -30561291.73 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -30561291.73
540039.6.9999999.C04100.C10000 | Stage 2 Unlet Works | Phase 2 - Construction Phase | Phase 2 - Construction Phase | F | CON | MWSTU | C | C04 | TN | DP | P2 | P2U | 540039.TN.DP.P2.P2U | Sinisa Galac | Sinisa Galac/ Natasha Juckes | HYB | 0 | 0 | 1101252167.91 | 1101252167.91 | 1101252167.91 | 0 | 1101841055.1091 | -588887.1991 | 329280628.95 | 1430532796.86 | 1332008126.45 | 1430532796.86 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 138320054.15 | 242922741.57 | 161612334.96 | 165420255.33 | 184606074.3 | 185669375.79 | 22701331.81 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4318645.96 | 4318645.96 | 15762338.12 | 15762338.12 | 15762338.12 | 27465249.29 | 27465249.29 | 27465249.29 | 26094338.47 | 26094338.47 | 26094338.47 | 17055496.72 | 17055496.72 | 17055496.72 | 29870743.83 | 15897218.55 | 15897218.55 | 17269351.69 | 17269351.69 | 17269351.69 | 16783964.88 | 16783964.88 | 16783964.88 | 14586116.61 | 14586116.61 | 14586116.61 | 10954625.44 | 10954625.44 | 10954625.44 | 11546071.39 | 11546071.39 | 11546071.39 | 13202866.39 | 13202866.39 | 13202866.39 | 13866942.68 | 13866942.68 | 13866942.68 | 14439729.39 | 14439729.39 | 14439729.39 | 13630546.65 | 13630546.65 | 13630546.65 | 14574372.54 | 14574372.54 | 14574372.54 | 13044149.89 | 13044149.89 | 13044149.89 | 15837208.93 | 15837208.93 | 15837208.93 | 18079626.74 | 18079626.74 | 18079626.74 | 18015820.35 | 18015820.35 | 18015820.35 | 14219630.01 | 14219630.01 | 14219630.01 | 11632813.49 | 11632813.49 | 11632813.49 | 18021528.08 | 18021528.08 | 18021528.08 | 4179403.7 | 4179403.7 | 4179403.7 | 1104971.13 | 1104971.13 | 1104971.13 | 806964.77 | 806964.77 | 806964.77 | 4427313.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.TU.TBC001 | Stage 2 Unlet Works | Stage 2 Early Works - Utilities & Programme De-risking | Stage 2 Early Works - Utilities & Programme De-risking | F | CON | MWSTU | C | C04 | TN | DP | P2 | P2U | 540039.TN.DP.P2.P2U | Sinisa Galac | Sinisa Galac/ Natasha Juckes | HYB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.9999999.C00200.C3X040 | Stage 2 Unlet Works | Contractor Fee - Tunnels | Contractor's fee - Prelims | F | CON | MWSTU | C | C04 | TN | DP | P2 | P2U | 540039.TN.DP.P2.P2U | Sinisa Galac | Sinisa Galac/ Natasha Juckes | HYB | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.9999999.C00300.C3X040 | Stage 2 Unlet Works | Contractor Fee - Tunnels | Contractor's fee - Direct Works | F | CON | MWSTU | C | C04 | TN | DP | P2 | P2U | 540039.TN.DP.P2.P2U | Sinisa Galac | Sinisa Galac/ Natasha Juckes | HYB | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 187371420.24 | 187371420.24 | 168941892.48 | 187371420.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.9999999.C00500.D1Y110 | Stage 2 Unlet Works | Environment Authority costs | Environment Authority costs | F | CON | TPOTH | C | C06 | TN | DP | P2 | P2U | 540039.TN.DP.P2.P2U | Sinisa Galac |  | HYB | 0 | 0 | 165507.4783 | 165507.4783 | 165507.4783 | 0 |  | 165507.4783 | -165507.4783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23543.2128 | 36701.1075 | 78947.3684 | 26315.7895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1961.9344 | 1961.9344 | 1961.9344 | 1961.9344 | 1961.9344 | 1961.9344 | 1961.9344 | 1961.9344 | 1961.9344 | 1961.9344 | 1961.9344 | 1961.9344 | 3058.4256 | 3058.4256 | 3058.4256 | 3058.4256 | 3058.4256 | 3058.4256 | 3058.4256 | 3058.4256 | 3058.4256 | 3058.4256 | 3058.4256 | 3058.4256 | 6578.9474 | 6578.9474 | 6578.9474 | 6578.9474 | 6578.9474 | 6578.9474 | 6578.9474 | 6578.9474 | 6578.9474 | 6578.9474 | 6578.9474 | 6578.9474 | 2192.9825 | 2192.9825 | 2192.9825 | 2192.9825 | 2192.9825 | 2192.9825 | 2192.9825 | 2192.9825 | 2192.9825 | 2192.9825 | 2192.9825 | 2192.9825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.9999999.C00500.C22700 | Stage 2 Unlet Works | Work for Local Authorities | Work for Local Authorities | X | CON | STATS | C | C05 | TN | DP | P2 | P2U | 540039.TN.DP.P2.P2U | Sinisa Galac | Future | HYB | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 783808.74 | 783808.74 | 7752578.48 | 783808.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.9999999.C06100.D1Y044 | Stage 2 Unlet Works | Rail Authority costs | Rail Authority costs | X | CON | TPRAI | C | C06 | TN | DP | P2 | P2U | 540039.TN.DP.P2.P2U | Sinisa Galac | Bob Jheeta / Warren Pavett | HYB | 0 | 0 | 158887.1791 | 158887.1791 | 158887.1791 | 0 |  | 158887.1791 | -158887.1791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22601.4843 | 35233.0632 | 75789.4737 | 25263.1579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1883.457 | 1883.457 | 1883.457 | 1883.457 | 1883.457 | 1883.457 | 1883.457 | 1883.457 | 1883.457 | 1883.457 | 1883.457 | 1883.457 | 2936.0886 | 2936.0886 | 2936.0886 | 2936.0886 | 2936.0886 | 2936.0886 | 2936.0886 | 2936.0886 | 2936.0886 | 2936.0886 | 2936.0886 | 2936.0886 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 6315.7895 | 2105.2632 | 2105.2632 | 2105.2632 | 2105.2632 | 2105.2632 | 2105.2632 | 2105.2632 | 2105.2632 | 2105.2632 | 2105.2632 | 2105.2632 | 2105.2632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.9999999.C00500.D1Y041 | Stage 2 Unlet Works | TBC - future stages | TU- Non- Contestable- Construction, Utilities Power | F | CON | STATS | C | C11 | TN | DP | P2 | P2U | 540039.TN.DP.P2.P2U | Sinisa Galac | Future | HYB | 30000 | 0 | 11069466.5337 | 11069466.5337 | 11069466.5337 | 0 |  | 11069466.5337 | 0.066252 | 11069466.6 | 0 | 11069466.6 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 7054658.8038 | 59183.9395 | 1977811.8952 | 1977811.8952 | 0 | 0 | 0 | 0 | 0 | 0 | -30000 | [25 empty] | 30000 | [13 empty] | 783850.9782 | 783850.9782 | 783850.9782 | 783850.9782 | 783850.9782 | 783850.9782 | 783850.9782 | 783850.9782 | 783850.9782 | 0 | 0 | 0 | 19727.9798 | 19727.9798 | 19727.9798 | 0 | 0 | 0 | 0 | 0 | 0 | 164817.6579 | 164817.6579 | 164817.6579 | 164817.6579 | 164817.6579 | 164817.6579 | 164817.6579 | 164817.6579 | 164817.6579 | 164817.6579 | 164817.6579 | 164817.6579 | 164817.6579 | 164817.6579 | 164817.6579 | 164817.6579 | 164817.6579 | 164817.6579 | 164817.6579 | 164817.6579 | 164817.6579 | 164817.6579 | 164817.6579 | 164817.6579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [47 empty] | -30000
540039.6.9999999.C00500.D1Y045 | Stage 2 Unlet Works | TBC - future stages | TU- Non- Contestable- Construction, Utilities Telecoms | F | CON | STATS | C | C12 | TN | DP | P2 | P2U | 540039.TN.DP.P2.P2U | Sinisa Galac | Future | HYB | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 152640.75 | 152640.75 | 0 | 152640.75 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.9999999.C00500.D1Y046 | Stage 2 Unlet Works | TBC - future stages | TU- Non- Contestable- Construction, Utilities Water | F | CON | STATS | C | C13 | TN | DP | P2 | P2U | 540039.TN.DP.P2.P2U | Sinisa Galac | Future | HYB | 0 | 0 | 167114 | 167114 | 167114 | 0 |  | 167114 | -1492.85 | 165621.15 | 167114.01 | 165621.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48117.8306 | 84626.2905 | 34369.879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4009.8192 | 4009.8192 | 4009.8192 | 4009.8192 | 4009.8192 | 4009.8192 | 4009.8192 | 4009.8192 | 4009.8192 | 4009.8192 | 4009.8192 | 4009.8192 | 7052.1909 | 7052.1909 | 7052.1909 | 7052.1909 | 7052.1909 | 7052.1909 | 7052.1909 | 7052.1909 | 7052.1909 | 7052.1909 | 7052.1909 | 7052.1909 | 2864.1566 | 2864.1566 | 2864.1566 | 2864.1566 | 2864.1566 | 2864.1566 | 2864.1566 | 2864.1566 | 2864.1566 | 2864.1566 | 2864.1566 | 2864.1566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540039.6.9999999.C00500.D1Y043 | Stage 2 Unlet Works | TBC - future stages | TU- Non- Contestable Others- (Nominate - new connections) CA03 and CA05 | F | CON | STATS | C | C13 | TN | DP | P2 | P2U | 540039.TN.DP.P2.P2U | Sinisa Galac | Future | HYB | 0 | 0 | 19589203.74 | 19589203.74 | 19589203.74 | 0 |  | 19589203.74 | 0 | 19589203.74 | 13901634.25 | 19589203.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410779.1886 | 3165138.0422 | 9610582.2821 | 5488537.6915 | 890418.6936 | 23747.842 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42740.1793 | 71234.0591 | 73607.8019 | 73607.8019 | 66484.0116 | 83105.3348 | 142466.8373 | 147215.6037 | 142466.8373 | 147215.6037 | 147215.6037 | 246942.2617 | 294431.2075 | 284933.6745 | 294431.2075 | 294431.2075 | 360916.5001 | 662471.4978 | 641101.4082 | 662471.4978 | 641101.4082 | 662471.4978 | 886856.158 | 890418.6936 | 920098.8043 | 890418.6936 | 920098.8043 | 884482.4153 | 764571.8985 | 846491.0025 | 819184.6345 | 846491.0025 | 819184.6345 | 441648.0922 | 441648.0922 | 427400.5118 | 441648.0922 | 427400.5118 | 283746.1626 | 184019.5047 | 172146.948 | 184019.5047 | 178083.2263 | 162649.415 | 71234.0591 | 73607.8019 | 73607.8019 | 71234.0591 | 73607.8019 | 42740.1793 | 36803.9009 | 36803.9009 | 33242.6463 | 36803.9009 | 23747.842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Carbon
540039.XXXXXXXXXX | Carbon | Tunnels Carbon | Tunnels Carbon | X | CON | TPRAI | C | C06 | TN | CT | PL | CAR | 540039.TN.CT.PL.CAR |  |  |  | 0 | 0 | 43800000.9965 | 43800000.9965 | 43800000.9999 | -0.003334 | 43800001 | -0.003455 | -43800000.9965 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 14325.3333 | 2410756 | 8663865.0001 | 7466543.6665 | 7288069.3332 | 8038635.3333 | 8287191.3333 | 1630614.9968 | 0 | 0 | [56 empty] | 3581.3333 | 3581.3333 | 3581.3333 | 3581.3333 | 3581.3333 | 26395.3333 | 26395.3333 | 26395.3333 | 26395.3333 | 26395.3333 | 26395.3333 | 346314.6667 | 346314.6667 | 346314.6667 | 604929.3333 | 604929.3333 | 604929.3333 | 716090 | 716090 | 716090 | 747177.6667 | 747177.6667 | 747177.6667 | 709336.6667 | 709336.6667 | 709336.6667 | 770561.3333 | 770561.3333 | 770561.3333 | 748903.3333 | 748903.3333 | 748903.3333 | 650835 | 650835 | 650835 | 488797.3333 | 488797.3333 | 488797.3333 | 515187.6667 | 515187.6667 | 515187.6667 | 589114 | 589114 | 589114 | 618745.3333 | 618745.3333 | 618745.3333 | 644303 | 644303 | 644303 | 608197.3333 | 608197.3333 | 608197.3333 | 650311 | 650311 | 650311 | 582032 | 582032 | 582032 | 706659 | 706659 | 706659 | 806716 | 806716 | 806716 | 803869 | 803869 | 803869 | 634482.3333 | 634482.3333 | 634482.3333 | 519058 | 519058 | 519058 | 804123.6667 | 804123.6667 | 804123.6667 | 186485.6667 | 186485.6667 | 186485.6667 | 49304 | 49304 | 49304 | 36007 | 36007 | 36007 | 11101.33 | 0
NR VAT
540039.6.9999999.C14R00.R11000 | NR VAT | Tunnels - NR VAT on Inflation | Tunnels - NR VAT on Inflation | F | CON | NRVAT | C | C14 | TN | CT | PL | VAT | 540039.TN.CT.PL.VAT | Sinisa Galac |  | VAT | 51752.7459 | 0 | 62526972.5735 | 62526972.5735 | 62526972.5735 | 0 |  | 62526972.5735 | -27200036.9135 | 35326935.66 | 67432357.25 | 35326935.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 394091.4652 | 499146.4331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61633734.6752 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25496.6069 | 26256.1389 | 30990.2948 | 22280.9955 | 27170.2239 | 27333.6451 | 27192.1924 | 36916.4629 | 36620.0262 | 50736.7749 | 39692.5884 | 43405.5152 | 35250.9777 | 31685.1551 | 24357.1092 | 40914.1877 | 41880.1685 | 37838.1129 | 36035.9592 | 38353.5656 | 40143.0858 | 67377.4255 | 51609.0652 | 53701.6207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61633734.6752
540039.6.XXXXX03.C080NR.D1Y100 | NR VAT | Tunnels - Advanced Works NR VAT | Tunnels - Advanced Works NR VAT | V | EEW | NRVAT | C | C08 | TN | CT | PL | VAT | 540039.TN.CT.PL.VAT | Sinisa Galac | Sinisa Galac | VAT | 33433.8078 | 848186.0241 | 9938164.983 | 10786351.0071 | 10786351.0071 | 0 | 340694377.2683 | -329908026.2612 | 353175492.8629 | 363961843.87 | 317549673.76 | 363113657.8459 | 1030.4 | 1030.4 | 0 | 25822.8341 | 25822.8341 | 0 | 2157637.7 | -1335274.51 | 25822.8341 | 61671.6585 | 662.4 | 14462.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9861368.5245 | 9865.28 | 7524.72 | -128.1 | 2389.96 | 2700.96 | 4518.37 | 3291.65 | -1366375.72 | 1779.34 | 1491.15 | 2520.11 | -4852.23 | 2565.63 | 1876.61 | -14255.02 | -237.71 | 2974.37 | -7408.72 | -921.21 | 1916.13 | 2234.21 | 39264.18 | -3216.0359 | 1030.4 | 0 | 33433.8078 | 13842.9254 | 13953.3254 | 0 | 110.4 | 0 | 110.4 | 0 | 110.4 | 0 | 110.4 | 0 | 110.4 | 0 | 110.4 | 0 | 110.4 | 0 | 110.4 | 0 | 110.4 | 0 | 110.4 | 0 | 110.4 | 0 | 110.4 | 6900 | 7010.4 | 0 | 110.4 | 0 | 110.4 | 0 | 110.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9861368.5245
540039.6.XXXXX04.C080NR.D1Y100 | NR VAT | Tunnels - Construction NR VAT | Tunnels - Construction NR VAT | V | CON | NRVAT | C | C08 | TN | CT | PL | VAT | 540039.TN.CT.PL.VAT | Sinisa Galac | Sinisa Galac | VAT | 637845.568 | 713505.8234 | 260378969.9308 | 261092475.7542 | 261092475.7542 | 0 |  | 261092475.7542 | -261055675.7542 | 36800 | 0 | -676705.8234 | 345329.7666 | 345329.7666 | 0 | 713505.8234 | 713505.8234 | 0 | 0 | 0 | 713505.8234 | 4995733.8048 | 5975300.8116 | 29527859.5456 | 55333841.6915 | 38152956.2502 | 37777965.7991 | 41820790.4281 | 41893432.1328 | 8326910.6924 | 2202976.4531 | 0 | -5628797.6783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368176.0567 | 345329.7666 | 314505.312 | 323340.256 | 381011.376 | 273482.88 | 332944.688 | 334394.976 | 332115.952 | 450141.3536 | 629790.4896 | 616621.0208 | 481601.9183 | 525783.5825 | 426301.2355 | 382546.8064 | 293587.6659 | 492344.7544 | 503138.003 | 453828.211 | 431500.6215 | 458494.7886 | 479096.2056 | 802804.3347 | 613909.8592 | 637748.3257 | 362406.8653 | 251257.2607 | 151763.9037 | 100120.761 | 863404.7612 | 881754.4663 | 3263453.1184 | 3261705.5723 | 3263453.1184 | 5682862.337 | 5695095.6308 | 5750581.7504 | 5619875.2956 | 5633028.3425 | 5629096.246 | 3996210.7222 | 4482164.1669 | 4038153.0062 | 6322025.7296 | 3745435.9377 | 3750897.078 | 4048669.7073 | 4026606.1723 | 4041679.2874 | 3944469.253 | 3949493.6247 | 3944469.253 | 3387511.0541 | 3832177.7213 | 3384889.4993 | 2582080.9453 | 2579459.3905 | 2553026.9902 | 2665854.3564 | 2663669.806 | 2665854.3564 | 3001106.0858 | 2998266.2645 | 2981445.839 | 3129168.3956 | 3573835.0628 | 3128731.6269 | 3256207.0256 | 3250527.383 | 3249435.1078 | 3069966.093 | 3069310.8221 | 3069966.093 | 3276895.3596 | 3272525.7567 | 3272525.7567 | 2933136.9662 | 3377803.6335 | 2933136.9662 | 3552610.8245 | 3552610.8245 | 3552610.8245 | 4032311.1719 | 4032311.1719 | 4032311.1719 | 4018159.524 | 4018159.524 | 4018159.524 | 3176200.7104 | 3620867.3776 | 3176200.7104 | 2602469.4762 | 2602469.4762 | 2602469.4762 | 4019425.4446 | 4019425.4446 | 4019425.4446 | 1685374.2221 | 949374.2662 | 949374.2662 | 1187494.4423 | 712161.1096 | 267494.4423 | 201399.4737 | 201399.4737 | 201399.4737 | 1200230.2368 | 385604.643 | 385604.643 | 385604.643 | 363474.362 | 363474.362 | 363474.362 | 363474.362 | 363474.362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5628797.6783
[17 empty] | 4652554.5219 | 13241788.3512 | 2734871605.6458 | 2748113393.997 | 2748113394.0004 | -0.003334 | 2754401971.9117 | -6288577.9147 | 183608699.173 | 2931722093.17 | 3014301046.71 | 2918480304.8188 | 2416431.5976 | 2416431.5976 | 0 | 6509275.7631 | 6509275.7631 | 0 | 7231986.2527 | -499473.6646 | 6509275.7631 | 35079197.627 | 41665922.9314 | 270850802.6222 | 513788014.2895 | 376954485.2674 | 386560211.6941 | 436797138.4601 | 444093420.4267 | 84294184.5944 | 29784970.0931 | 0 | 115003257.6399 | 274339.27 | 209129.5873 | -35066.75 | 186029.93 | 163932.15 | 133068.41 | 120173.0112 | -1380288.79 | 60567.34 | 46938.15 | 58085.778 | -336381.7512 | 29834.7115 | 22637.4685 | 7892.2733 | -45740.5396 | 122434.8822 | -377753.135 | -163124.58 | 66012.63 | 63730.71 | 1809707.17 | 2557212.5746 | 2416431.5976 | 2187838.4347 | 2464716.0873

## In-month Summary
Account | FY 2024_25 In-month | FY 2025_26 In-month | May-24 In-month | YTD In-month
Other Client Scope | 355972.5172 | 0 | 3078 | 6156
Project Inflation | 2911480.5823 | 3449008.8662 | 170008.7806 | 357196.1898
Contractor Fee | 0 | 0 | 0 | 0
Stage 1 Scope | 27320560.2 | 18916923.01 | 1615810 | 3394890
Risk Quota | 0 | 0 | 0 | 0
Project Risk | 0 | 111530.4027 | 0 | 0
Project Opportunities | 0 | 0 | 0 | 0
Incentives | 1000000 | 0 | 0 | 0
Utilities (Client) | 3600 | 3600 | 600 | 600
Stage 2 Unlet Works | 30000 | 12719700.5201 | 2000000 | 0
Carbon | 0 | 0 | 0 | 0
NR VAT | 5818376.8471 | 6476940.355 | 329267.4076 | 691626.9629

## ABP Summary
Account | FY 2024_25 ABP | FY 2025_26 ABP | May-24 ABP | YTD ABP
Other Client Scope | 331572.0572 | 0 | 181105.4772 | 181105.4772
Project Inflation | 2141801.4413 | 2712752.3539 | 142696.4073 | 281264.9231
Contractor Fee | 0 | 0 | 0 | 0
Stage 1 Scope | 26120727.2 | 24803230.01 | 1727284 | 3436552
Risk Quota | 0 | 0 | 0 | 0
Project Risk | 0 | 111530.4027 | 0 | 0
Project Opportunities | 0 | 0 | 0 | 0
Incentives | 1000000 | 0 | 0 | 0
Utilities (Client) | 3600 | 3600 | 600 | 600
Stage 2 Unlet Works | 30000 | 7559700.5201 | 30000 | 30000
Carbon | 0 | 0 | 0 | 0
NR VAT | 5451496.9285 | 6475109.6447 | 383030.2027 | 723032.1217

## In-month
Account | May-24 In-month | May-24 ABP | Variance
Other Client Scope | 3078 | 181105.4772 | -178027.4772
Project Inflation | 170008.7806 | 142696.4073 | 27312.3733
Contractor Fee | 0 | 0 | 0
Stage 1 Scope | 1615810 | 1727284 | -111474
Risk Quota | 0 | 0 | 0
Project Risk | 0 | 0 | 0
Project Opportunities | 0 | 0 | 0
Incentives | 0 | 0 | 0
Utilities (Client) | 600 | 600 | 0
Stage 2 Unlet Works | 2000000 | 30000 | 1970000
Carbon | 0 | 0 | 0
NR VAT | 329267.4076 | 383030.2027 | -53762.7951

## YTD
Account | YTD In-month | YTD ABP | Variance
Other Client Scope | 6156 | 181105.4772 | -174949.4772
Project Inflation | 357196.1898 | 281264.9231 | 75931.2667
Contractor Fee | 0 | 0 | 0
Stage 1 Scope | 3394890 | 3436552 | -41662
Risk Quota | 0 | 0 | 0
Project Risk | 0 | 0 | 0
Project Opportunities | 0 | 0 | 0
Incentives | 0 | 0 | 0
Utilities (Client) | 600 | 600 | 0
Stage 2 Unlet Works | 0 | 30000 | -30000
Carbon | 0 | 0 | 0
NR VAT | 691626.9629 | 723032.1217 | -31405.1587

## 2024_25
Account | FY 2024_25 In-month | FY 2024_25 ABP | Variance
Other Client Scope | 355972.5172 | 331572.0572 | 24400.46
Project Inflation | 2911480.5823 | 2141801.4413 | 769679.141
Contractor Fee | 0 | 0 | 0
Stage 1 Scope | 27320560.2 | 26120727.2 | 1199833
Risk Quota | 0 | 0 | 0
Project Risk | 0 | 0 | 0
Project Opportunities | 0 | 0 | 0
Incentives | 1000000 | 1000000 | 0
Utilities (Client) | 3600 | 3600 | 0
Stage 2 Unlet Works | 30000 | 30000 | 0
Carbon | 0 | 0 | 0
NR VAT | 5818376.8471 | 5451496.9285 | 366879.9186

## 2025_26
Account | FY 2025_26 In-month | FY 2025_26 ABP | Variance
Other Client Scope | 0 | 0 | 0
Project Inflation | 3449008.8662 | 2712752.3539 | 736256.5124
Contractor Fee | 0 | 0 | 0
Stage 1 Scope | 18916923.01 | 24803230.01 | -5886307
Risk Quota | 0 | 0 | 0
Project Risk | 111530.4027 | 111530.4027 | 0
Project Opportunities | 0 | 0 | 0
Incentives | 0 | 0 | 0
Utilities (Client) | 3600 | 3600 | 0
Stage 2 Unlet Works | 12719700.5201 | 7559700.5201 | 5160000
Carbon | 0 | 0 | 0
NR VAT | 6476940.355 | 6475109.6447 | 1830.7103

## In-month_TOTALS
Account | May-24 In-month | May-24 ABP | Variance
Totals | 4118764.1882 | 2464716.0873 | 1654048.1009

## YTD_TOTALS
Account | YTD In-month | YTD ABP | Variance
Totals | 4450469.1528 | 4652554.5219 | -202085.3692

## 2024_25_TOTALS
Account | FY 2024_25 In-month | FY 2024_25 ABP | Variance
Totals | 37439990.1467 | 35079197.627 | 2360792.5196

## 2025_26_TOTALS
Account | FY 2025_26 In-month | FY 2025_26 ABP | Variance
Totals | 41677703.154 | 41665922.9314 | 11780.2226